## Civil
| Supplier’S NAME & ADDRESS:M/s | FIELD QUALITY PLAN |  |  |  | PROJECT: BRBCL Nabinagar PACKAGE : Construction of PQC work from Ash Dyke Lagoon-01 to Lagoon-02( Phase -02). P.O .NO. : MAIN CONTRACTOR :
|  | ITEM : CIVIL WORKS |  | QP NO:
|  |  |  | REV NO: | 0
DATE:
|  | SUB SYSTEM: |  | PAGE 1 OF 5
Sl.No. | CHARACTERISTICS/ITEM | TYPE OF CHECK | INSTRUMENT | CLASS OF CHECK | QUANTUM/FREQUENCY OF CHECK | REFERENCE DOC. AND ACCEPTANCE STD. | FORMAT OF RECORDS | REMARKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | GENERAL REQUIRMENTS
1.1 | Setting up of Filed QA & QC laboratory | Physical | As Required | A | Once prior to start of work | Tech Specs and Const. Drawing. | SR/Report | Functioning of laboratory equeipment in proper working condition to be verified on Monthly basis if Lab setup done by Vendor
1.2 | Avialability of requiste laboratory set up and equipment in good working condition well before commencement of concerned activity | Physical | As Required | A | Once prior to start of work and thereof monthly/ calibration thereof once In 6 month | Tech Specs and Const. Drawing. | SR/Report | Calibration of All equipment-by Owner approved NABL/ third party agency
1.3 | Availability of QA & QC manpower based on deployment schedule | Physical | As Required | A | Once prior to start of work and thereof monthly | Tech Specs and Const. Drawing. | SR/Report
1.4 | Sampling for testing of building materials concrete mix design etc | Physical | As Required | A | Once per each source | Tech Specs and Const. Drawing. | SR/TR | Approved Third Party Lab
2 | BATCHING PLANT
2.1 | Deployment | visual/Acceptance | As required | B | Once prior to start of work | Tech Specs and Const. Drawing. | SR | Automatic concrete batching plant shall be computerised with electronic display and Printer attchment
2.2 | Mixer efficiency | visual/Acceptance | As required | B | Once per shift of concreting | Tech Specs and Const. Drawing. |  | percentage variation in the quantities of concrete ingradients in every batch time of mixing will be as given in IS:457
2.3 | Calibration | visual/Acceptance | As required | A | Once prior to start of concrete work and thereof once In 6 month | Tech Specs and Const. Drawing. |  | Calibration of Batching plant-by Owner approved NABL/ third party agency
3 | EXCAVATION AND FILLING IN SOIL
3.1 | Initial ground Lvl. / Layout/Final Pit/ Bed level | Measurement | Auto Lvl. / Theodolite / Total Stn. | B | 100% | As per Technical/ CPWD specification | SR
3.2 | Side Slope during Excavation | Measurement | As Required | B | Random | As per Technical/ CPWD specification | SR
3.3 | Standard proctor test to determine optimum moisture content and max.dry density of fill | Test | As Required | A | Once after filling | As per IS 2720 | TR | Approved Third Party Lab
3.4 | Moisture content of fill before compaction | Test | As Required | A | Once after filling | As per IS 2720 | SR/TR | To be compacted in layers 300mm each layer
4 | COARSE AGGREGATE FOR CONCRETING
4.1 | Sieve analysis (particles size and shape) | Test | IS Sieve set | B | One sample per 100cu.m. or change of source whichever is earlier | IS:383,IS:2386-1963 Part-1 | Test Report
4.2 | Crushing value, impact value | Test | As per IS code | A | One sample per 100cu.m. or change of source whichever is earlier | IS:2386-1963 and IS:383 Part 2,4,5,&7 | -do-
4.3 | Flakiness Index Elongation Index | Test | As per IS code | B | One sample per 100cu.m. or change of source whichever is earlier | IS:2386 part-1 | Test Report
4.4 | Moisture Content | Test | As Required | B | Start of concrete | Tech Specs and Const. Drawing.IS | TR
5 | FINE AGGREGATE (SAND)
5.1 | Sieve analysis (particles size and shape) | Test | IS Sieve set | B | Once for 100cu.m. or change of source whichever is earlier | IS:383-1970,IS:2386 Part-1 | Test Report
5.2 | Moisture Content/silt content | Test | As Required | B | Start of concrete | Tech Specs and Const. Drawing.IS | Test Report/SR
LEGEND TO BE USED :-
Class -A = Critical, B = Major, C = Minor, SR = Site Register, TR = Test Report, TC = Test Certificate, CHP = Customer hold point.
Class -A Checks shall be witnessed by NTPC FQA, B checks by Civil Department & survillance by NTPC FQA and for C checks survillance by Civil Deptt.
FOR NTPC USE ONLY
Supplier's / Contractors Stamp and signature |  | Reviewed By |  |  | Approved By |  | Stamp and Date
| Supplier’S NAME & ADDRESS:M/s | FIELD QUALITY PLAN |  |  |  | PROJECT: BRBCL Nabinagar PACKAGE :Construction of PQC work from Ash Dyke Lagoon-01 to Lagoon-02( Phase -02). P.O .NO. : MAIN CONTRACTOR :
|  | ITEM : CIVIL WORKS |  | QP NO:
|  |  |  | REV NO: | 0
DATE:
|  | SUB SYSTEM: |  | PAGE 1 OF 2
Sl.No. | CHARACTERISTICS/ITEM | TYPE OF CHECK | INSTRUMENT | CLASS OF CHECK | QUANTUM/FREQUENCY OF CHECK | REFERENCE DOC. AND ACCEPTANCE STD. | FORMAT OF RECORDS | REMARKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
6 | MIX CONCRETE/ RCC/PRECAST
6.1 | Trial Mix( Cube compressive strenth) Mix Design | As required | Physical | A | Min. 4 Trial Mixes with admixtures and without admixtures | IS :516 &IS:1062/NTPC Tech Spec. |  | Mix Design NTPC Approved LabThird party
6.2 | Compressive strength | Test | Cube testing M/C | A | One per 50cum or part thereof for each | IS:456-2000, IS:516-1959 Tech. Spec. | Test Report | Min. of 6 cubes for each mix, 3 specimen shall be tested at 7 days remaining 3 shall be for 28 days comp.
6.3 | Admixture | visual | Verification & TC | A | 100% | IS/NTPC specification & construction Drawings | Site register & MTC | Approved material(NTPC)
6.4 | Water Proofing systems | visual | Verification & TC | A | 100% | IS/NTPC specification & construction Drawings | Site register & MTC | Approved material(NTPC)
6.5 | Casting of cube | Physical | Verification | B | IS:456-2001 | IS:456-2000, IS:516-1959 Tech. Spec. | SR
6.6 | Workability (slump) | Test | Slump cones | B | One sample every two hours from each mixer | IS:456 and Tech spec. | Test Report
6.7 | Curing | visual | As required | B | 100% | Relevant IS & CPWD specification | Site register
7 | REINFORCMENT STEEL
7.1 | Material Verification & TC review | visual | Verification & TC | A | 100% | Relevant IS & CPWD specification | Site register & MTC | Approved material(NTPC)
7.2 | Cutting ,bending , placing of reinforced steel bars & lapping | Measurement | As required | B | Physical | 100% |  | Drawing/Bar bending schedule
7.3 | Acceptance • Cover, spacing of bars, spacers and chairs after the reinforcement cage is put inside the formwork | Physical / Measurement | As required | B | Physical | 100% |  | -do-
8 | FORMWORK: SHUTTERING
8.1 | Check for material (to be approved by EIC) | Visual | Visual | B | 100% | IS/CPWD/NTPC specification & construction Drawings | SR
8.2 | Position, dimensions and verticality of form work before concreting | Measurement | Measurement | B | 100% | -do- | -do-
8.3 | CHECK FOR JOINTS : To avoid loss of liquid the joints should be leak proof as far as possible. | Visual | Visual | C | 100% | -do- | -do-
9 | BRICK WORK AND PLASTER WORK
9.1 | Test on Brick | Dimension & shape | -do- | B | As per IS | IS/CPWD/NTPC specification & construction Drawings | TR
9.2 |  | Compressive strength & Water Absorption | -do- | A | As per IS | IS/CPWD/NTPC specification & construction Drawings | TR
9.3 | Brick Work | Workmanship | Visuval | B | IS/CPWD Spe. | IS/CPWD/NTPC specification | Site register
LEGEND TO BE USED :-
Class -A = Critical, B = Major, C = Minor, SR = Site Register, TR = Test Report, TC = Test Certificate, CHP = Customer hold point.
Class -A Checks shall be witnessed by NTPC FQA, B checks by Civil Department & survillance by NTPC FQA and for C checks survillance by Civil Deptt.
FOR NTPC USE ONLY
Supplier's / Contractors Stamp and signature |  | Reviewed By |  |  | Approved By |  | Stamp and Date
| Supplier’S NAME & ADDRESS:M/s | FIELD QUALITY PLAN |  |  |  | PROJECT: BRBCL Nabinagar PACKAGE : Construction of PQC work from Ash Dyke Lagoon-01 to Lagoon-02( Phase -02). P.O .NO. : MAIN CONTRACTOR :
|  | ITEM : CIVIL WORKS |  | QP NO:
|  |  |  | REV NO: | 0
DATE:
|  | SUB SYSTEM: |  | PAGE 1 OF 3
Sl.No. | CHARACTERISTICS/ITEM | TYPE OF CHECK | INSTRUMENT | CLASS OF CHECK | QUANTUM/FREQUENCY OF CHECK | REFERENCE DOC. AND ACCEPTANCE STD. | FORMAT OF RECORDS | REMARKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
10 | Granular Sub -Base(GSB)
10.1 | Gradation | As agreed/ Required | Physical | B | One test per 200cum | IS: 2386 (part-1) Tech spacs const.drawing, section 900 of Morth specfication | TR
10.2 | Aggegate Impact Value | As agreed/ Required | Physical | A | One test per 200cum | IS: 2286 (part-4) Tech spacs const.drawing, section 900 of Morth specfication | TR
10.3 | Atterberg Limits | As agreed/ Required | Physical | A | One test per 400cum | IS: 2720 (part-5) Tech spacs const.drawing, section 900 of Morth specfication | TR | Approved Lab Third party Test
10.4 | Deleterious Content | As agreed/ Required | Physical | A | Once for each source | IS: 2720 (part-27) Tech spacs const.drawing, section 900 of Morth specfication | TR | Approved Lab Third party Test
10.5 | CBR | As agreed/ Required | Physical | A | One test per 400cum | IS: 2720 (part-16) Tech spacs const.drawing, section 900 of Morth specfication | TR | Approved Lab Third party Test
11 | DLC(Dry Lane Concrete)Coarse Aggregate
11.1 | Sieve analysis (particles size and shape) | Test | IS Sieve set | B | One sample per 100cu.m. or change of source whichever is earlier | As per Tech Specs and Const. Drawings. Section 900 of MORTH Specification | Test Report
11.2 | Crushing value, impact value | Test | As per IS code | A | One sample per 200cu.m. or change of source whichever is earlier | As above | Test Report
11.3 | Flakiness Index & Elongation Index | Test | As per IS code | B | One sample per 200cu.m. or change of source whichever is earlier | As above | Test Report
11.4 | Water Absorption | Test | As per IS code | A | One sample per 200cu.m. or change of source whichever is earlier | As above | Test Report
11.5 | Soundness | Test | As per IS code | A | Once for each source | As above | Test Report
11.6 | Alkali Aggregate Reactivity | Test | As per IS code | A | Once for each source | As above | Test Report
12 | FINE AGGREGATE (SAND)
12.1 | Sieve analysis (particles size and shape) Deleterious Material | Test | IS Sieve set | B | Once for 100cu.m. or change of source whichever is earlier | As above | Test Report
13 | DLC ( CONCRETE)
13.1 | Design Mix | Test | As per IS code | A | Morth Section-V-Section 600 | As above | Test Report | Mix Design NTPC Approved LabThird party
13.2 | 4 Trial mixes to ascertain the workability and cube strength after receiving the recommended Mix design from specialist agency. | Physical | As per IS code | A | Each mix proportion | As above | Site register & Lab
13.3 | Concrete Cube compressive strength | Test | As per IS code | A | 3 Sample for each 1000sqm or part thereof laid each day | As above | Site register & Lab
13.4 | In-Situ Density | Test | As per IS code | A | One sample per 2000 sqm or part there of | As above | Test Report
13.5 | Workability (slump) | Test | As per IS code | B | At the timeof concrete pouring at site every two hrs | As above | Site register & Lab
13.6 | W/C Ratio | Test | As per IS code | B | For each batch of Concrete | As above | Site register & Lab
13.7 | Placement of concrete, compacting, curing | Physical | As per IS code | B | At Random | As above | Site register & Lab
13.8 | Thickness of Concrete | Physical | As per IS code | B | At Random | As above | Site register & Lab
13.9 | Aligmnment & Surface regularity both transverselyand longitudinally | Physical | As per IS code | B | Once a day or one day's work | As above | Site register & Lab
LEGEND TO BE USED :-
Class -A = Critical, B = Major, C = Minor, SR = Site Register, TR = Test Report, TC = Test Certificate, CHP = Customer hold point.
Class -A Checks shall be witnessed by NTPC FQA, B checks by Civil Department & survillance by NTPC FQA and for C checks survillance by Civil Deptt.
FOR NTPC USE ONLY
Supplier's / Contractors Stamp and signature |  | Reviewed By |  |  | Approved By |  | Stamp and Date
| Supplier’S NAME & ADDRESS:M/s | FIELD QUALITY PLAN |  |  |  | PROJECT: BRBCL Nabinagar PACKAGE : Construction of PQC work from Ash Dyke Lagoon-01 to Lagoon-02( Phase -02). P.O .NO. : MAIN CONTRACTOR :
|  | ITEM : CIVIL WORKS |  | QP NO:
|  |  |  | REV NO: | 0
DATE:
|  | SUB SYSTEM: |  | PAGE 1 OF 4
Sl.No. | CHARACTERISTICS/ITEM | TYPE OF CHECK | INSTRUMENT | CLASS OF CHECK | QUANTUM/FREQUENCY OF CHECK | REFERENCE DOC. AND ACCEPTANCE STD. | FORMAT OF RECORDS | REMARKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
14 | PQC(Pavement Quality Concrete) Coarse Aggregate
14.1 | Sieve analysis (particles size and shape) | Test | IS Sieve set | B | One sample per 100cu.m. or change of source whichever is earlier | As per Tech Specs and Const. Drawings. Section 900 of MORTH Specification | Test Report
14.2 | Crushing value, impact value | Test | As per IS code | A | One sample per 200cu.m. or change of source whichever is earlier | As above | Test Report
14.3 | Flakiness Index Elongation Index | Test | As per IS code | B | One sample per 200cu.m. or change of source whichever is earlier | As above | Test Report
14.4 | Water Absorption | Test | As per IS code | A | One sample per 200cu.m. or change of source whichever is earlier | As above | Test Report
14.5 | Soundness | Test | As per IS code | A | Once for each source | As above | Test Report
14.6 | Alkali Aggregate Reactivity | Test | As per IS code | A | Once for each source | As above | Test Report
15 | FINE AGGREGATE (SAND)
15.1 | Sieve analysis (particles size and shape) Deleterious Material | Test | IS Sieve set | B | Once for 100cu.m. or change of source whichever is earlier | As above | Test Report
16 | PQC ( CONCRETE)
16.1 | Design Mix | Test |  | A | Morth Section-V-Section 600 | As above | Test Report | Mix Design NTPC Approved LabThird party
16.2 | 4 Trial mixes to ascertain the workability and cube strength after receiving the recommended Mix design from specialist agency. | Physical | As required | A | Each mix proportion | As above | Site register & Lab
16.3 | Concrete Cube compressive strength | Test | As required | A | 2 Cube & 2 Beam per 150cum and part there of | As above | Site register & Lab
16.4 | Concrete Flexural Strengh test | Test | As required | A | 2 Cube & 2 Beam per 150cum and part there of | As above | Site register & Lab
16.5 | Workability (slump) | Test | As required | B | At the timeof concrete pouring at site every two hrs | As above | Site register & Lab
16.6 | Water Cement Ratio | Test | As required | B | For each batch of Concrete | As above | Site register & Lab
16.7 | Placement of concrete, compacting, curing | Physical | As required | B | At Random | As above | Site register & Lab
16.8 | Thickness of Concrete | Physical | As required | B | At Random | As above | Site register & Lab
16.9 | Aligmnment & Surface regularity both transverselyand longitudinally | Physical | As required | B | Once a day or one day's work | As above | Site register & Lab
17 | CEMENT | Material Verification & TC Review & Cpmressive strenth | As required/week wise | A | 100% | IS/CPWD/NTPC specification & construction Drawings | Site register & MTC | BIS Approved
17.1 | Storage | visual | As required | B | As per IS | *Covered shed & Protection from water/rain .if cement is stored more than 60 days in go-down of contractor, same shall be retested for comp. strength and setting time.
18 | M.S. Round Dowel Bars & Plastic sheet of 1.25 mm for dowel bars | Material Verification & TC Review & Cpmressive strenth | As required | A | 100% | As per IS, CPWD,IRC,Morth Specs/NTPC Specification | Site register & MTC
19 | Tie Bars | Material Verification & TC Review & Cpmressive strenth | As required | A | A | As per IS, CPWD,IRC,Morth Specs/NTPC Specification | Site register & MTC
20 | Seperation Membrane | Material Verification & TC Review & Cpmressive strenth | As required | A | At Random | As per IS, CPWD,IRC,Morth Specs/NTPC Specification | Site register & MTC
21 | Sealing Compound | Material Verification & TC Review & Cpmressive strenth | As required | A | 100% | As per IS, CPWD,IRC,Morth Specs/NTPC Specification | Site register & MTC
LEGEND TO BE USED :-
Class -A = Critical, B = Major, C = Minor, SR = Site Register, TR = Test Report, TC = Test Certificate, CHP = Customer hold point.
Class -A Checks shall be witnessed by NTPC FQA, B checks by Civil Department & survillance by NTPC FQA and for C checks survillance by Civil Deptt.
FOR NTPC USE ONLY
Supplier's / Contractors Stamp and signature |  | Reviewed By |  |  | Approved By |  | Stamp and Date
| Supplier’S NAME & ADDRESS:M/s | FIELD QUALITY PLAN |  |  |  | PROJECT: BRBCL Nabinagar PACKAGE : Construction of PQC work from Ash Dyke Lagoon-01 to Lagoon-02( Phase -02). P.O .NO. : MAIN CONTRACTOR :
|  | ITEM : CIVIL WORKS |  | QP NO:
|  |  |  | REV NO: | 0
DATE:
|  | SUB SYSTEM: |  | PAGE 1 OF 5
Sl.No. | CHARACTERISTICS/ITEM | TYPE OF CHECK | INSTRUMENT | CLASS OF CHECK | QUANTUM/FREQUENCY OF CHECK | REFERENCE DOC. AND ACCEPTANCE STD. | FORMAT OF RECORDS | REMARKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
22 | Premoulded joint filler for expansion joints having impregnation more than 35% | Material Verification & TC Review | As required | A | 100% | As per Morth Specs/ NTPC Specification | Site register & MTC
23 | Water for Concrete | Test | As required | A | 100% | As per IS, CPWD,IRC,Morth Specs/NTPC Specification |  | Approved Lab Third party Test
24 | Chemical Admixture | Material Verification & TC Review | As required | A | 100% | As per IS, CPWD,IRC,Morth Specs/NTPC Specification | Site register & MTC
25 | PVC Pipes | Material Verification & TC Review | As required | A | 100% | As per IS & CPWD Specification | Site register & MTC | Approved material(NTPC)
26 | OTHER ALL BOUGHT OUT ITEMS | As agreed/required | Verification & TC | A | 100% | Relevant IS & CPWD | Site register/MTC | Approved material(NTPC)
LEGEND TO BE USED :-
Class -A = Critical, B = Major, C = Minor, SR = Site Register, TR = Test Report, TC = Test Certificate, CHP = Customer hold point.
Class -A Checks shall be witnessed by NTPC FQA, B checks by Civil Department & survillance by NTPC FQA and for C checks survillance by Civil Deptt.
FOR NTPC USE ONLY
Supplier's / Contractors Stamp and signature |  | Reviewed By |  |  | Approved By |  | Stamp and Date
1. In case of non availability of equipment for any test, such tests are required to be done at Govt./NTPC approved laboratory.
2. Relevant Standard and specification shall prevail over Quality Plan in case of contradiction if any.
3. All the Relevant Codes/ other specifications required as reference document should be arranged /submitted by Agency at the time of Execution.