PRICE ADJUSTMENT

(NOT APPLICABLE)

(i)	The Contract price shall be subject to price adjustment during performance of the Contract to reflect changes in the cost of labour and material components etc. in accordance with the provisions described below:

(ii)	The price adjustment provisions shall be applicable separately for price components relating to Supply of Equipment including spare parts, Installation, Civil and allied Works, as per price break-up furnished by the Contractor in Schedule-2/ Schedule-6 and Schedule-4. The Price Adjustment shall be without any Ceiling.

(iii)	Only following components of the Contract Price will be subject to Price adjustment:

(a)	Ex-Works (India) Price of Plant and Equipment including Mandatory Spares manufactured within the Employer's Country, but excluding Type Tests Charges (covered in Schedule 2)

(b)	Installation Price Component of Contract Price (covered in Schedule 4) consisting of Erection portion.

(c)	Civil Works price component of Contract Price (covered in Schedule-4) excluding Demolition of existing structures (if applicable) price.

(d)	Site Fabricated Structural Works price component of Contract Price (covered in Schedule-4).

(e)	Ex-Works (India) Price of Recommended Mandatory Spares manufactured within the Employer's Country (covered in Schedule-6).

(iv)	Price adjustment amounts towards aforesaid components of Contract Price shall be paid in the respective currencies of Contract.

(v)	The indices for price adjustment shall necessarily be of the country of origin of goods/labour and shall be well established and nationally recognised in that country. Preferably Government indices shall be used. For the purpose of this contract, country of origin shall be India.

(vi)	The price adjustment formula for the components of the Contract Price, as mentioned at Sl.No. (iii) above shall be as stipulated hereinafter.

(vii)	Ex-Works Price Component of Plant and Equipments including spares, but excluding Type Tests Charges

It is understood that the price component of the equipments for any shipment/despatch comprises of a fixed portion (designated as 'F' and the value of which is specified hereunder) and a variable portion linked with the indices for various materials and labour (description and co-efficients as enumerated below).

The amount of price adjustment towards variable portion payable/recoverable on each shipment/despatch shall be computed as under :

EC = EC1 - EC0

EC1 will be computed as follows :

A1                        B1	                C1                                                  L1

EC1=  EC0   {  F  +  a  x  -----  +  b  x  ----- +  c   x  ------ + .............+ Lb x --------}

A0                        B0	                 C0                               L0

Where

EC	=	Adjustment to Ex-Works Price Component expressed in the currency of the Contract payable to the contractor for each shipment/despatch.

EC1	=	Adjusted Amount of Ex-Works Price Component expressed in the currency of the Contract payable to the Contractor for each shipment/despatch.

ECo	=	Ex-Works Price for the plant and equipments in the currency of the Contract, shipment/despatch wise.

-	The fixed portion of the Ex-Works Component of the Contract Price (F) shall be 0.15

-	a,b,c etc. shall be co-efficients of major materials/items involved in the Ex-Works Component of the Contract Price. The sum of these co-efficients shall be between 0.50 to 0.60.

-	A,B,C etc. shall be published price indices of corresponding major materials/items. Such indices shall necessarily be of the country of origin of goods.

-	'Lb" shall be co-efficient for labour component in the Ex-Works Component of the Contract Price which shall be between 0.25 to 0.35

'L' shall be labour index.

-	Sum of all the material co-efficients and the labour co-efficient shall be 0.85

For the indices, subscript 'o' refers to indices as on 30 days prior to date of opening of Techno-Commercial bids.

Subscript '1' refers to indices as of :

(a)	three months prior to the date of shipment/despatch for labour, and

(b)	at the expiry of two third (2/3) period from the date of Notification of Award to the date of shipment/despatch, for material.

For the purpose of this clause the date of shipment/despatch shall mean the schedule date of shipment/despatch or actual date of shipment/despatch, whichever is earlier. The schedule date of shipment/despatch shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

In case of shipments/dispatches which are delayed beyond the schedule date of shipment/despatch for reasons attributable to the Contractor the price adjustment provision shall not be applicable for the period of time between the schedule date of shipment/despatch and the actual date of shipment/despatch.  For this purpose, the schedule date of shipment/despatch shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

(viii)	For Installation Price Component (excluding Civil Works and Site Fabricated Structural Works component) of the Contract:

It is understood that the price component for erection portion of Installation Services comprises a fixed portion and variable portion linked with the index of labour (description and co-efficients as enumerated).

The monthly price adjustment amount for the erection portion of Installation Services component will be computed as per the formula given below :

ER = ER1 - ERo

ER1 will be computed as follows :

L1                           W1

ER1 = ERo (F* +  0.5 x Lb* x -----   + 0.5 x Lb* x  ------ )

L0                           W0

Where :

ER	=	Adjustment  to  Installation  Price  component  expressed  in    Indian Rupees payable to the contractor for each billing.

ER1 =	Adjusted amount of Installation services component of Contract Price expressed in Indian Rupees payable to the Contractor.

ER0 =	Value of the Installation work done in the billing period, which shall be calculated as under :

For the purpose of computing ERo, each installation bill (which is excluding Initial Advance and amount payable on completion of Guarantee Test) during the Installation period upto the 'Completion of the Facilities' shall be divided by a factor as indicated below:

Installation component of the Contract

Price		-	[Initial Advance amount +				Installation  component  of the

Contract	Price	payable	on

successful	completion	of Guarantee Test]

---------------------------------------------------------------------------------

Installation component of the Contract Price

The payment of price adjustment amount so computed shall be made against a separate invoice, linking the corresponding invoice for Installation payment after retaining the pro-rata amount due on completion of the Guarantee Test. The amounts so retained shall be paid on successful completion of Guarantee Tests.

F = Fixed Price component = ……*…….

Lb = Coefficient of labour (for all categories) = ……*…….

L = Indian field labour index Namely, All India Consumer Price Index for Industrial Workers (All India Monthly Average) as published by Labour Bureau, Shimla, Government of India.

W = Arithmetical average of Minimum Wages for Unskilled, Skilled, Semi- skilled and Highly skilled workers notified by the Central Government for the particular classified Area in which the project site is located or notified by the State Government of the state in which the project site is located, whichever is higher

Subscript 'o' refers to indices / minimum wages as on 30 days prior to deadline set for opening of Envelope-I (Techno-commercial) Bids.

Subscript '1' refers to the indices / minimum wages as applicable for the month of execution of the Installation work.

In case there is a revision in  the  applicable  minimum  wages  during  a month, calculation of 'W1' would take into consideration the weighted average of the applicable wages (wage before revision and wage after revision) and the number of days of applicability of such wages in the month.

# For the purpose of this clause, month of execution of installation work shall mean the schedule month of execution of the installation work or actual month of execution of the installation work, whichever is earlier. The schedule date for completion of a particular installation activity shall be as identified in line with provisions of Time schedule, Appendix-4 to the Contract Agreement.

In case of installation activities which are delayed beyond the schedule date for reasons attributable to the contractor, the price adjustment provision shall not be applicable for the period of time between the schedule date of completion and actual date of completion of the respective installation activity. For this purpose, the schedule date for completion of a particular installation activity shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

(*Value of components to be specified by concerned package coordinator)

(ix)	Site Fabricated Structural Works Price Component

Price adjustment for Structural Works component of the Contract Price

It is understood that the Structural Works Price Component comprises a fixed portion (designated as 'F' and the value of which is specified hereunder) and variable portion linked with the indices for various materials and labour (description and coefficients as enumerated below).

The amount of price adjustment towards variable portion payable/recoverable shall be computed as follows :

ESW = ESW1 - ESWo

ESW1 will be computed as follows :

ESW1 = ESWo {F+ a x (A 1  / Ao) + b x (B 1  / Bo) + c x (C 1  / Co) + d x (D 1 / Do) + 0.5 x Lb x (L 1 / Lo) + 0.5 x Lb x (W 1 / Wo) }

Where,

ESW  =	Adjustment to Structural Works Price Component expressed

in the currency of the Contract.

ESW1 =	Adjusted   amount  of  Structural  Works  Price    Component expressed in the currency of the Contract.

For the purpose of computing ESWo, each structural bill (which is excluding initial advance and amount payable on completion of Guarantee test) during the structural work period upto the completion of the facilities' shall be divided by a factor as indicated below :

Structural Component of the	-	{Initial Advance amount + structural component     contract price		of the contract price payable after successful

completion of Guarantee Test}

————————————————————————————————————

Structural Component of the Contract Price

The payment of price adjustment amount so computed shall be made against a separate invoice, linking the corresponding invoice for Structural Work Portion of Installation payment after retaining the pro-rata amount due on Completion of the Guarantee Tests. The amount so retained shall be paid on successful completion of the Guarantee Tests.

F =	The fixed portion of the Structural Works Price Component shall be

…..*…...

- a, b, c & d shall be co-efficient of major materials/items involved in the Structural Works Price Component of the Contract Price.

- A, B, C, D shall be published price indices of corresponding major material/items.

- "Lb" shall be co-efficient for labour component for Structural Works Price Component of Contract Price which shall be …..*…...

- L shall be Labour Index, namely, Consumer Price Index for Industrial Workers (Gen.) applicable to "All India" as published by Labour Bureau. Shimla of the Govt. of India.

- W shall be Arithmetical average of Minimum Wages for Unskilled, Skilled, Semi-skilled and Highly skilled workers notified by the Central Government for the particular classified Area in which the project site is located or notified by the State Government of the state in which the project site is located, whichever is higher.

Subscript '0' refers to indices/minimum wages as on 7 days prior to deadline set for opening of Envelope-I (Techno-commercial) Bids.

Subscript '1' refers to the indices/minimum wages as applicable for one month prior to the month of execution of the structural work except "Structural Steel". For structural steel the index, '1' refers to the indices as applicable for 90 days prior to the month of execution of the structural work.

In case there  is  a  revision  in  the  applicable  minimum  wages  during  a month, calculation of 'W1' would take into consideration the weighted average of the applicable wages (wage before revision and wage after revision) and the number of days of applicability of such wages in the month.

For the purpose of this clause, month of execution of structural work shall mean the schedule month of execution of the structural work or actual month of execution of Structural Work, whichever is earlier. The schedule date for completion shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

In case of Structural Works activities which are delayed beyond the schedule date for reasons attributable to the contractor, the price adjustment provision shall not be applicable for the period of time between the schedule date of completion and actual date of completion of the respective Structural activity. For this purpose, the schedule date for completion of a particular Structural activity shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

(*To be specified by concerned package coordinator)

(x)	Price adjustment for Civil Works component of the Contract Price (including construction materials)

The prices quoted by the bidder shall be base price, which will be subjected to price adjustment in accordance with the conditions and formula prescribed herein and further subject to satisfying the requirement specified in this clause.

A fixed percentage of the civil works component of the contract price shall be firm and shall not be subject to any price adjustment. The balance portion of the civil works component of the contract price shall be subject to price adjustment on account of changes in materials and labour as detailed below:

CV = CV1 - CV0

CV1 will be computed as follows :

CV1 = CVo {F + m x (M1 / Mo) + d x (D 1  / Do) + s x (S 1  / So) + c x (C 1 / Co) + 0.5 x Lb x (L 1 / Lo) + 0.5 x Lb x (W 1 / Wo)}

Where,

CV	=	Adjustment to civil works component expressed in the   currency of the contract payable to the contractor for each billing period.

CV1 =	Adjusted contract price i.e. value of work done after  application of above price adjustment formula in the billing period.

CVo  = Base contract price, subject to price adjustment, i.e. the value of the work done in the billing period as per the monthly billing schedule for which the price adjustment is to be calculated.

CVo shall be calculated as under :

Each Civil Works bill (which is excluding initial advance and amount payable on completion of Guarantee test) during the Civil Works period upto the completion of the facilities' shall be divided by a factor as indicated below :

Civil Works Component of the contract price	-{Initial  Advance  amount +

Civil Works component of the contract price payable after successful completion of Guarantee Test}

—————————————————————————————————

Civil Works Component of the Contract Price

The payment of price adjustment amount so computed shall be made against a separate invoice, linking the corresponding invoice for Civil Works Portion of Installation payment after retaining the pro-rata amount due on Completion of the Guarantee Tests. The amount so retained shall be paid on successful completion of the Guarantee Tests.

F = Fixed portion of the contract price which will not be subjected to any adjustment under this formula or otherwise which will be …..*…...

m = Coefficient of material (excluding cement & steel) content in the  cost of civil portion of the work which will be …..*…...

d = Coefficient of High Speed Diesel Oil (P.O.L) content in the cost of civil portion of the work which will be …..*…...

s = Coefficient of steel content in the cost of civil portion of work which will be …..*…...

c = Coefficient of cement content in the cost of civil portion of work which will be …..*…...

Lb =	Coefficient of labour (for all categories) content in the cost of civil portion of the work which will be …..*…...

M = Material Index, namely, Index No. of wholesale price under group. "All commodities" as published by office of the Economic Adviser, Government of India.

D =  High Speed Diesel Oil price, namely price of High Speed diesel  oil, at Pump Station of India Oil Corporation nearest to the project site. (selling price inclusive of taxes and duties as per litre of H.S.D. Oil).

S = Index for steel content shall be *“Mild Steel-Long Products”/ “Mild Steel-Flat Products”, as published by Ministry of Commerce and Industry, GOI .

C = Index for cement content shall be *“Pozzolana cement”, as published by Ministry of Commerce and Industry, GOI.

L = Labour Index, namely, Consumer Price Index for Industrial Workers (Gen.) applicable to "All India" as published by Labour Bureau. Shimla of the Govt. of India.

W = Arithmetical average of Minimum Wages for Unskilled, Skilled, Semi- skilled and Highly skilled workers notified by the Central Government for the particular classified Area in which the project site is located or notified by the State Government of the state in which the project site is located, whichever is higher.

Subscript

'o' = Refers, to the values of above mentioned minimum wages, labour / material/steel/cement indices, or diesel price as on 7 days prior to deadline set for opening of Envelope-I (Techno-commercial) Bids.

'1' = Refers to values of corresponding minimum wages, labour / material/steel/cement indices, or diesel price as applicable for the month prior to month in which the work is executed.

In case there is a revision in  the  applicable  minimum  wages  during  a month, calculation of 'W1' would take into consideration the weighted average of the applicable wages (wage before revision and wage after revision) and the number of days of applicability of such wages in the month.

For the purpose of this clause, month of execution of civil work shall mean the schedule month of execution of Civil work or actual month of execution of Civil Work, whichever is earlier. The schedule date for completion shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

In case of Civil Works activities which are delayed beyond the schedule date for reasons attributable to the contractor, the price adjustment provision shall not be applicable for the period of time between the schedule date of completion and actual date of completion of the respective Civil Work activity. For this purpose, the schedule date for completion of a particular Civil Work activity shall be as identified in line with provisions of Time Schedule, Appendix-4 to the Contract Agreement.

(*To be specified by concerned package coordinator)

(xi)	The value of co-efficients and the source of applicable indices and their base values for the purpose of computing price adjustment under the contract shall be as under:

A.	Ex-Works Price Component of Plant and Equipments including spares, but excluding Type Tests Charges

-----------------------------------------------------------------------------------------------------------------------------

S.No.		Item	Value of	Name of 	Value of Base Date

Coefficient	published	Indices (as on 30

index and	days prior to date of

its origin	opening of Technical  bids)

-----------------------------------------------------------------------------------------------------------------------------

Material

1.	….	a = 	......................	...............................

2.	….	b = 	......................	.................................

3.	……………	c=

Labour	lb =	......................	.................................

Fixed Complement	F = 0.15	......................	................................

-----------------------------------------------------------------------------------------------------------------------------

i)	Sum of all material coefficients a,b, c indicated above shall be between 0.50 to.0.60.

ii)	The labour coefficient "l" shall be between 0.25 to 0.35.

iii)	Sum of all material coefficients and labour coefficients shall be 0.85

iv)	Sum of F, a,b, c & I should be equal to 1.0.

B.	Installation Price Component *

-----------------------------------------------------------------------------------------------------------------------------

Sl.	Item	Value of	Name of Published	Value of Indices as

No.		Co-efficient	Index and its origin	on 30 days prior to

date of submission

of Envelope-II (Price) Bid.

-----------------------------------------------------------------------------------------------------------------------------

1.	Fixed Portion	F = 0.15 	-------------	----------

2.	Indian Field	0.85	All India Consumer	-----------

Labour (F) :		Price Index for Industrial

workers (All Indian average)

published by Labour Bureau,

Shimla, Govt. of India.

Labour (W):		Arithmetical average of	---------------

Minimum Wages for Unskilled, Skilled, Semi-Skilled and highly skilled Workers notified by the Central Government for the particular classified Area in which the project site is located or notified by the State Government of the state in which the project site is located, whichever is higher.

-----------------------------------------------------------------------------------------------------------------------------

--------------------------------------------------------------------------------------------------------------------

C.	Civil Works Price Component*

--------------------------------------------------------------------------------------------------------------------

Item  Index	Value of	Name of published	Value of Coefficients	index and its	Base date

origin	Indices (as on

7 days) prior to date of opening of Techno-Commercial Bids

--------------------------------------------------------------------------------------------------------------------

Fixed Portion  F = 0.20

  - Labour

    - 0.5 x Lb = 0.5 x 0.25	Consumer price index for industrial

workers (All India General) as published by Labour Bureau, Shimla.

    - 0.5 x Lb = 0.5 x 0.25   Arithmetical average of

Minimum Wages for Unskilled, Skilled, Semi-skilled and Highly skilled workers notified by the Central Government for the particular classified Area in which the project site is located or notified by the State Government of the state in which the project site is located, whichever is higher

  - Material  m = 0.15	Index no. of wholesale Price under (excluding	group "All Commodities" as published

cement &	by Ministry of Commerce and Industry,

steel)	GOI

  - High	d = 0.05	Price of high speed diesel oil per Speed		litre at the Indian Oil Corpn. outlet

Diesel	nearest to the project (selling price inclusive of taxes & duties, if any)

  - Steel	s = 0.25	Index for " MS Wire Rods " under sub-

group of " Mild Steel -Long Products " under Group of " Manufacture of Basic Metals " as published by Ministry of Commerce and Industry, GOI.

  - Cement  c = 0.10	Index for " Pozzolana Cement " under sub- group of

" Manufacture of cement, lime and plaster " under Group of "Manufacture of other Non-Metallic Mineral Products" as published by Ministry of Commerce and Industry, GOI.

--------- -------------------------------------------------------------------------------------------------------------------

D	Site Fabricated Structural Works Price Component*

-----------------------------------------------------------------------------------------------------------------------------

Item	Coefficient	Value of	Name of	Value of Coefficients	published	Base

index and	Indices (as on

its origin	7 days prior to date of opening of Techno-Commercial Bids)

-----------------------------------------------------------------------------------------------------------------------------

Material :

- Hot Rolled Coils	(a)	0.50	Index for "Hot Rolled (HR)

& Sheets	Coils & Sheets, including

Narrow Strip” under sub-group of "Mild Steel -Flat Products" under Group of "Manufacture of Basic Metals" as published by Ministry of Commerce and Industry, GOI

- Manufacture of	(b)	0.15	Index for "Manufacture of fabricated Metal			structural metal products”

Products-Structural	under Group of "Manufacture

Metal Product	of Fabricated metal products, except Machinery and Equipment" as published by Ministry of Commerce and Industry, GOI

- Labour :

  - 0.5 x l = 0.5 x 0.15 Consumer price index for industrial workers (All India General) as published by Labour Bureau, Shimla.

  - 0.5 x l = 0.5 x 0.15	Arithmetical average of Minimum Wages for Unskilled, Skilled, Semi-skilled and Highly skilled workers notified by the

Central Government for the particular classified Area in which the project site is located or notified by the State Government of the state in which the project site is located, whichever is higher

- Fixed Component :	Fs	0.20

-----------------------------------------------------------------------------------------------------------------------------

- The above information shall be filled in at the time of Contract Agreement signing based on price adjustment data offered by the bidder in Attachment-4P to Bid Form of Price Bids and/or as mutually discussed and agreed upon.