## Milestone Payment Formula
Project : Western Offshore Pipe laying Rate Contract (WOPL-RC)
Ref | Activity | Weightage | Amount of Col. B in Quoated Currency derived for each season | Milestone % | Milestone % | Milestone for Payment | Milestone Amount
| (A) | (B) | (C ) | (D) |  | (E) | (F)
1 | INSURANCE
1.1 | Insurance | 3.11 % of I.A of instant season |  | 85 | 85 | a) Upon submission of certificate of insurance (Cover Note) for insurance policy(s) specific for the Season wise Value for the firm scope of work of the project and its acceptance by Company in terms of clause 7.3.13.1.(a),(b)&(c) of GCC and proof of 100% premium paid to Insurance Company.
|  |  |  | 15 | 15 | b) Upon submission of insurance policy(s) specific for the Season wise Value for the firm scope of work of the project and its acceptance by Company in terms of clause 7.3 of GCC.
2 | SURVEY
2.1 | Submarine Pipelines and Risers/ OFC/Umbilical | 92.89% of S.SURP of Table II-A3 of instant season |  | 40 | 40 | a) Upon completion of pre-engineering survey and submission of complete survey report and its acceptance by Company.
|  |  |  | 20 | 20 | b) Upon completion of pre-installation survey and submission of complete survey report and its acceptance by Company.
|  |  |  | 40 | 40 | c) Upon completion of post- installation survey and submission of complete survey report and its acceptance by Company.
*For pipeline segments, data of Pipeline route corridor survey will be shared by company and payment towards milestone no.2.1(a) shall be made along with milestone no.2.1(b).
3 | DESIGN AND ENGINEERING
3.1 | Submarine Pipelines and Risers | 92.89% of S.DESP of Table II-A3 of instant season |  | 100 | 100 | a) Upon progressive completion of engineering as approved and certified by Company.
4 | PROCUREMENT OF EQUIPMENT & MATERIALS
4.1 | Subsea WN Flange/Subsea Swivel Flange/Subsea Ball Valve /Flow TEE/ Subsea Piggable wye TEE/Associated subsea Bulk Item ( KAMOS gasket or equavalent gasket, fastners etc.) | 20 % of 92.89% of I.A(i) b) of Table A-3 I.A, I.B, I.C & I.D of instant season |  | 5 | 5 * | a) Upon progressive placement of LOI and acceptance by vendor.
|  |  |  | 5 | 10 * | b1). 5% Upon progressive approval of prelim Purchase Specifications at 1st Stage, for PS items, as applicable. #
|  |  |  | 5 |  | b2). 5% Upon progressive approval of final Purchase Specification at 2nd Stage, for PS items, as applicable. #
|  |  |  | 60 | 60 | c) Upon progressive dispatch from vendor works and submission of inspection & dispatch documents.
|  |  |  | 20 | 20 | d) Upon progressive arrival at fabrication yard/site submission of material test certificates and test reports, verification by TPI/CA and acceptance by Company.
|  |  |  | 5 | 5 | e) Upon progressive submission of release note of Certification Agency and clearance of punch points related to the above procurement milestones, if any
4.2 | Procurement of material for crossings, (milestone will be paid after completion of all crossings of each segment) | 20 % of 92.89% of S.CROSS of Table II-A3 of instant season |  | 85 | 85 | a) Procurement of Crossings Materials and arrival at yard/offshore
|  |  |  | 15 | 15 | b) Completion of procurement related punch points.
4.3 | Procurement of material for freespan (milestone will be paid after completion of all freespan of each segment) | 20% of 92.89% of S.FREE of Table II-A3 of instant season |  | 85 | 85 | a) Procurement of Freespan Material and arrival at yard/offshore
|  |  |  | 15 | 15 | b) Completion of procurement related punch points.
Note:-
* Applicable where the selected vendor is from ONGC’s vendor list or where PQD has already been approved by ONGC before placement of LOI. For others, where PQD is not approved before LOI, payment against milestones a & b above (i.e placement of LOI & upon approval of PS) will be issued together and Contractor will get 15% on completion of milestone ‘a’ and ‘b’ together.
# For non-PS-items, 10% above (b1 & b2) shall be clubbed with dispatch of material milestone (c)
1) Basis for milestone achievement for Sl. No. 5.1 to 5.3 shall be as per PS/MTO quantity for order placement per pipeline segment scope of work, this shall be based on design and engineering.
5 | FABRICATION - STRUCTURAL & NON-STRUCTURAL
5.1 | New riser protectors / barge bumpers (Includes procurement & fabrication) | 20 % of 92.89% of iv) of I.A(i) c) TABLE-I PART C of instant season |  | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
5.2 | Subsea Mudmats/Skids including Piling (Includes procurement & fabrication) | 20 % of 92.89% of v) of I.A(i) c) of TABLE-I PART C of instant season |  | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
5.3 | Jacket Strengthning- Steel (Includes procurement & fabrication) | 20% of 92.89% of xv) of I.A(i) c) of TABLE-I PART C of instant season |  | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
5.4 | Jacket Strengthening - Grout (Includes procurement & fabrication) | 20 % of 92.89% of xvi) of I.A(i) c) of TABLE-I PART C of instant season |  | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
6 | TRANSPORTATION AND INSTALLATION
6.1 | Submarine Pipelines/OFC/Umbilical | 92.89% of S.INSP of Table II-A3 of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of installation/ laying of each pipeline segment.
|  |  |  | 10 | 10 | c) Upon adjustments of variations and completion of punchpoints if any, of each pipeline segment /respective item.
6.2 | Installation of risers (including fabrication of riser bends, riser clamps, sub-sea tie-in spools etc. ) | 92.89% of S.INSRI of Table II-A3 of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon progressive completion of riser and I/J Tube installation and spool tie in.
|  |  |  | 10 | 10 | c) Upon submission of release note by certification agency and completion of punch points related to Installation, if any.
6.3 | Installation of New riser protectors / New barge bumpers / | 80% of 92.89% of iv) of I.A(i) c) of TABLE-I PART C of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon progressive completion of riser and I/J Tube installation and spool tie in.
|  |  |  | 10 | 10 | c) Upon submission of release note by certification agency and completion of punch points related to Installation, if any.
6.4 | Installation of Subsea Mudmats/Skids including Piling (including 4 nos. Piling) | 80% of 92.89% of v) of I.A(i) c) of TABLE-I PART C of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon progressive completion of riser and I/J Tube installation and spool tie in.
|  |  |  | 10 | 10 | c) Upon submission of release note by certification agency and completion of punch points related to Installation, if any.
6.5 | Jacket Strengthning- Steel | 80% of 92.89% of xv) of I.A(i) c) of TABLE-I PART C of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon progressive completion of riser and I/J Tube installation and spool tie in.
|  |  |  | 10 | 10 | c) Upon submission of release note by certification agency and completion of punch points related to Installation, if any.
7.8 | Jacket Strengthening - Grout | 92.89% of xvi) of I.A(i) c) of TABLE-I PART C of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon progressive completion of riser and I/J Tube installation and spool tie in.
|  |  |  | 10 | 10 | c) Upon submission of release note by certification agency and completion of punch points related to Installation, if any.
7.9 | Demolition of riser | 92.89% of S.DEMR of I.A(i) c) of Table II-A3 of instant season |  | 90 | 90 | a) Upon demolition of riser and two pipe-lengths
|  |  |  | 10 | 10 | b) Upon submission of proof of receipt for demolished material at NHAVA and completion of punch points.
7.1 | Installation of crossings, (milestone will be paid after completion of all crossings of each segment) | 80% of 92.89% of S.CROSS of Table II-A3 of instant season |  | 85 | 85 | a) Progressive payment segmentwise upon Installation of crossings
|  |  |  | 15 | 15 | b) Upon adjustments of variations and completion of punch points if any, of each pipeline segment /respective item
7.11 | Installation of freespan (milestone will be paid after completion of all freespan of each segment) | 80 % of 92.89% of S.FREE of Table II-A3 of instant season |  | 85 | 85 | a) Progressive payment segmentwise upon Installation of freespan.
|  |  |  | 15 | 15 | b) Upon adjustments of variations and completion of punchpoints if any, of each pipeline segment /respective item
7.12 | Installation of SPRUs (as applicable) | 92.89% of S.SPRU of Table II-A3 of instant season |  | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of installation on each pipeline segment
|  |  |  | 10 | 10 | c) Upon completion of punch points, if any
7.13 | Burial/Flush Burial/Dredging | 92.89% of vi- xiv of TABLE-I PART C of instant season |  | 100% | 100% | Upon progressive Completion and acceptance by Company
Note: 1. Basis of milestone achievement shall be per segment for pipelines, per demolition of riser and of riser protector with associated topside facilities. Milestones 7.1(c ), 7.4(b) and 7.5(b) to be raised after completion of all these activities of each pipeline.
8 | Testing/Pre- Commissioning and Commissioning assistance (wherever applicable and as per scope of work)
8.1 | Submarine Pipelines along with Riser/OFC/Umbilical | 92.89% of S.PRE of Table II-A3 of instant season |  | 80 | 80 | a) Upon completion of Hook-up, testing, pre-commissioning work of each segment
|  |  |  | 10 | 10 | b) Upon submission of test reports & its acceptance by Company
|  |  |  | 10 | 10 | c) Upon submission of Certificate of Approval for the respective facility from Certification Agency
9 | Liquidation of punch points
9.1 | Liquidation of punch points | 2.00% of I.A. of instant season |  | 100 | 100 | Upon completion of Punch Points related to Hookup, Pre-commissioning, commissioning activity, if any
10 | AS-BUILT DOCUMENTATION
10.1 | As Built for work to be completed in the scope of Contractor | 2.00% of I.A. of instant season |  | 100 | 100 | Payment upon submission of As-built drawing, documents, Software Files (as applicable) , Vendor dossiers, Operation & Maintenance Manuals etc. for the respective line segment in the project Scope and acceptance by Company as per GCC 5.1.9.3.
11 | Customs Duty | 100% of I.B. of Appendix A3 of instant season |  | 100 | 100 | Reimbursement at actual limited to the amount indicated herein on submission of documentary proof viz. bill of entry in original duly addressed by the Custom Authority and the amount of duty paid thereof along with relevant supporting documents subject however to provisions of change in law as per clause 7.6 (subsequent legislation) of GCC.
12 | Goods and Service Tax | 100% of I.C. of Appendix A3 of instant season |  | 100 | 100 | Payable at actual, limited to the amount indicated herein, along with relevant milestone as per invoice under Goods and Service Tax rules subject however to provisions of change in law as per clause no. 7.6 (Sub-sequent legislation) of GCC.
13 | Mob | 60% of 92.89% of I.A.(ii) of instant season |  | 100 | 100 | For season wise mobilization of each Marine Spread as indicated at I.A.(ii) of A-3 TABLE-I PART C of Price Schedule(A-3) , after getting all statutory clearances and subsequent deployment at site for offshore operation. Payment is dealt for each Marine spread seperately.
14 | Demob | 40 % of 92.89% of I.A.(ii) of instant season |  | 100 | 100 | When respective seaswise Marine Spread as indicated at I.A.(ii) of A-3 TABLE-I PART C of Price Schedule(A-3) has been demobilized from offshore at the end of the completion of the contract scope for each season.Payment is dealt for each Marine spread seperately.
|  | Total |  |  |  |  | 0
General Notes
1 | The line segments, along with their respective sizes and lengths as detailed in the A3/ Schedule of Rates (SOR), represent the indicative scope of work considered for evaluation of bids across three seasons. These quantities are used solely for comparative assessment during the bidding process. However, the actual scope of work—as identified and finalized by Company shall be communicated to the successful bidder prior to commencement of seasonal activities. Values for above Activities will be worked out based on finalized scope of work for each season for making payments as per above MPF. Payment shall be actual executed quantity based on unit rates quoted in Price Shcedule (A-3) and above MIlestone Payment Formula.
2 | Taxes and duties shall be paid in INR only.
3 | The requirement of dispatch / sail out wherever referred shall be the "Bill of Lading" for dispatch (as applicable) and certificate of carrier for sail out (as applicable).
4 | All yard and offshore related activities to be inspected and certified by Certification Agency / Third Party Inspection Agency.
5 | Release notes shall be issued by Certification Agency.
6 | Milestone to be submitted platform wise, pipeline segment wise and riser wise.
7 | Payment of transportation of pipelines and installation of pipeline with / without Robotic arm will be done together.
Note on A65: PANKAJ PATOWARY-81666: