# SCOPE OF WORK

# FOR

PIPELINE LAYING PROJECT (PLP)

TABLE OF CONTENTS

| Sub-Section | Title |
| --- | --- |
| 2.0 | Basic Bid Work- General Description |  |
| 2.1 | Survey |  |
| 2.2 | Submarine Pipelines |  |
| 2.3 | Description Of Facilities Modifications On Existing Well/Process Platforms |  |
| 2.4 | Contractor’s scope of supply |  |
| 2.5 | Quality Assurance |  |
| 2.6 | HSE Compliance |  |
| 2.7 | Responsibility of Company |  |
| 2.8 | Responsibility of Contractor |  |

  - BASIC BID WORK- GENERAL DESCRIPTION

This document is related to the installation of submarine pipelines and associated risers for Oil and Natural Gas Corporation Limited (ONGC), INDIA, hereinafter referred to as ‘ONGC’ or ‘Company’. ONGC is a leading player in the exploration and production of hydrocarbons, primarily engaged in the development of the Western Offshore Fields located in the Arabian Sea on the continental shelf of Western India. The infrastructure within these fields includes an extensive network of Wellhead Platforms (WHP), Process Platforms, Floating Production Storage and Offloading (FPSO) units, Mobile Offshore Production Units (MOPU), and pipelines.

The Western Offshore Fields are comprised of three primary assets: the Mumbai High (MH) Asset, the Neelam & Heera (N&H) Asset, and the Bassein & Satellite (B&S) Asset. ONGC has successfully executed numerous Engineering, Procurement, Construction, Installation, and Commissioning projects under Lump Sum Turnkey (LSTK) contracts within these fields. However, ONGC now intends to change the contracting strategy for execution of pipeline projects and hence plans to divide and disaggregate pipeline projects in 05 (five) distinct components/ work packages.

These components envisaged by ONGC are:

          - Line Pipe Procurement

          - SPRU Procurement

          - Coating, Storage and Fabrication

          - Hiring of Marine Spread for Pipeline Installation activities on Rate Contract Basis

          - Integrate Rate Contract for Topside Modifications

These contracts will be awarded for a duration of five years. Hiring of Marine Spread for Pipeline Installation activities will be on Rate Contract Basis

The current tender pertains specifically to the hiring of Marine Spread Contractor for Pipeline Installation activities on Rate Contract Basis, for the installation of approximately 993.1 kilometres of submarine pipeline, along with associated risers. The scope, quantities, and work details indicated herein are tentative and subject to revision based on project requirements and final confirmation by the Company.

This section of bid package defines in general terms, the major components of the facilities which will form among other things the Contractor’s scope of work. The basic scope of work is related to laying/replacement of submarine pipelines and riser installation under this contract. It shall be the responsibility of the Contractor to survey (except route corridor survey), design, engineer, procure (except free issue material i.e., coated (rigid) line pipes for subsea pipeline and risers), fabricate, load out, transport all items required (viz. flanges, fittings, specialty items, clamps, pipeline materials etc.), coat & wrap, install, hook-up, flushing & cleaning of the pipelines, hydro test, hook up with topside and make pipelines ready for commissioning and commissioning assistance.

The indicative scope of work for all Five seasons will be provided to the contractor as part of the bid package to facilitate the evaluation of bids across the five seasons. However, the actual scope of work—as identified and finalized by Company shall be communicated to the successful bidders well in advance for the commencement of seasonal activities.  Contractor shall have to undertake replacement of any unplanned emergency jobs during the period in which the barge is undertaking the job in offshore but such emergency jobs shall remain within +15% or reduced scope shall be within -10% of the originally awarded scope value of work planned for that working season.

The addition/ Deletion/ Substitution in the Scope of the work for a working would be confirmed to the Contractor well in advance without any change in the completion date.

The Contractor’s responsibility shall also include dismantling, removal and disposal of old risers, riser clamps, etc. All activities necessary to carry out the required works shall be undertaken in timely & safe manner.

The facilities with major components as described herein along with all the materials & equipment required to perform the functions described shall be designed, engineered, procured, supplied, fabricated, transported, installed, hooked up, tested & pre- commissioned by the Contractor as specified in tender unless otherwise stated. All equipment / items, Spreads, vessels, materials, consumables and labour necessary to provide & complete the works shall be the responsibility of the Contractor.

The descriptions provided in subsequent sections are intended to outline a tentative scope of work, which may be adjusted by the Company based on actual field conditions or operational requirements. The following sub-sections give a general description of the major components of the facilities envisaged under this project.

Section 2.1 of this document covers the survey requirements for sub-marine pipelines and for risers

Section 2.2 of this document covers the functional description of pipelines and risers as applicable and miscellaneous works as envisaged under scope of work.

Section 2.3 of this document covers the Contractors scope of Supply.

Section 2.4 of this document covers the Quality Assurance.

Section 2.5 of this document covers the requirement related with HSE compliance.

  - SURVEY REQUIREMENTS

    - All surveys related to pipeline laying, riser installation, and jacket face—excluding the route corridor survey—shall be within the contractor’s scope

    - Contractor shall be fully responsible for carrying out all the Pre-engineering, Pre-construction and Post- construction surveys for all jobs covered in this document including those related to pipelines and risers.

    - Detailed surveys including dive surveys needed for acquiring details of the pipelines where tie-ins are to be carried out for sectional replacement of the pipelines as per the scope of work. All surveys required for enabling such tie-ins are within the Contractor’s scope of work.

    - Any additional survey and investigation required to complete the work in all respect shall be the responsibility of the Contractor within in the lump sum contract price.

  - FUNCTIONAL DESCRIPTION- SUBMARINE PIPELINES & RISERS

The scope of work under this tender includes the complete replacement of certain existing pipelines, from riser top to riser top. In addition, partial replacement of pipelines, including their subsea tie-ins, is also covered. The scope further involves the installation of new pipelines along with their risers. The pipelines shall be rigid only.

    - SUBMARINE PIPELINES & RISERS SCOPE

The complete scope of work is scattered in three different western offshore fields’ viz. Mumbai High, Neelam & Heera and B&S Assets. Pipeline replacement will be carried out on a rolling plan basis through the hiring of the Marine Spread for Pipeline Installation activities for a period of 5 years, with free issue coated line pipes & riser pipes. Total indicative scope of laying/replacement/New of subsea pipeline is split in five (05) no of seasons.

The indicative Scope of Works for 5 seasons is as follows:

| For 5 seasons | WF | WI | GL | PB | Total |
| --- | --- | --- | --- | --- | --- |
| Segments | 104 | 14 | 28 | 1 | 147 |
| Length (Km) | 726.2 | 35.3 | 227.8 | 3.8 | 993.1 |

- All water injection pipeline (with risers) need to be liquid epoxy coated internally (Dia 6” and above).

- All well fluid pipelines (with risers) need to be FBE coated internally (Dia 8” and above).

      - The following list of segments and related data is indicative. The final scope and segment details shall be confirmed by the Company before commencement of work each season.

| 2.2.1.1.1 Season-I |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/n | Indicative Segments | Service | Proposed dia(inch) | Approx. length, (km) | New/Part/full replacement | No. of Risers to be installed | No. of risers to be removed | MOC for PL & Riser | Indicative Crossing Corrections | Indicative Free Span corrections |
| 1 | Segment 1 | GL | 6 | 5.5 | Full replacement | 2 | 2 | X-60 CS NACE | 21 | 5 |
| 2 | Segment 2 | WI | 6 | 3.2 | Full replacement | 2 | 2 | X-52 CS | 9 | 3 |
| 3 | Segment 3 | WI | 6 | 3.1 | Full replacement | 2 | 2 | X-52 CS | 8 | 3 |
| 4 | Segment 4 | WI | 6 | 2.9 | Full replacement | 2 | 2 | X-52 CS | 5 | 3 |
| 5 | Segment 5 | WI | 6 | 3.3 | Full replacement | 2 | 2 | X-52 CS | 9 | 3 |
| 6 | Segment 6 | WF | 16 | 4.7 | Full replacement | 2 | 2 | X-60 CS NACE | 2 | 5 |
| 7 | Segment 7 | WF | 16 | 6.9 | Full replacement | 2 | 2 | X-60 CS NACE | 1 | 7 |
| 8 | Segment 8 | GL | 8 | 9.8 | Full replacement | 2 | 2 | X-60 CS NACE | 2 | 10 |
| 9 | Segment 9 | GL | 6 | 3.7 | Full replacement | 2 | 2 | X-60 CS NACE | 1 | 4 |
| 10 | Segment 10 | WF | 8 | 7.9 | Full replacement | 2 | 0 | X-60 CS NACE | 2 | 8 |
| 11 | Segment 11 | WF | 14 | 10.7 | Full replacement | 2 | 0 | X-60 CS NACE | 9 | 11 |
| 12 | Segment 12 | WF | 14 | 6.2 | Full replacement | 2 | 0 | X-60 CS NACE | 10 | 6 |
| 13 | Segment 13 | WF | 12 | 8 | Full replacement | 0 | 0 | X-60 CS NACE | 21 | 8 |
| 14 | Segment 14 | GL | 6 | 2.8 | New | 2 | 0 | X-60 CS NACE | 0 | 3 |
| 15 | Segment 15 | WF | 6 | 7 | New | 2 | 0 | X-60 CS NACE | 14 | 7 |
| 16 | Segment 16 | WF | 12 | 19.9 | New | 2 | 0 | X-60 CS NACE | 3 | 20 |
| 17 | Segment 17 | WF | 10 | 10.2 | New | 2 | 0 | X-60 CS NACE | 5 | 10 |
| 18 | Segment 18 | WF | 10 | 7 | New | 2 | 0 | X-60 CS NACE | 6 | 7 |
| 19 | Segment 19 | WF | 14 | 28 | New | 2 | 0 | X-60 CS NACE | 4 | 28 |
| 20 | Segment 20 | GL | 6 | 3.1 | New | 2 | 0 | X-60 CS NACE | 1 | 3 |
| 21 | Segment 21 | GL | 6 | 8.2 | New | 2 | 0 | X-60 CS NACE | 3 | 8 |
| 22 | Segment 22 | GL | 4 | 9.9 | New | 2 | 0 | X-60 CS NACE | 7 | 10 |
| 23 | Segment 23 | GL | 4 | 7 | New | 2 | 0 | X-60 CS NACE | 6 | 7 |
| 24 | Segment 24 | GL | 6 | 6.3 | New | 2 | 0 | X-60 CS NACE | 7 | 6 |
| 25 | Segment 25 | WF | 12 | 1.2 | Part replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 26 | Segment 26 | WF | 20 | 2 | Part replacement | 2 | 2 | X-60 CS NACE | 1 | 1 |
| 27 | Segment 27 | WF | 22 | 2 | Part replacement | 2 | 2 | X-60 CS NACE | 1 | 1 |
| 28 | Segment 28 | WF | 24 | 2 | Part replacement | 2 | 2 | X-60 CS NACE | 1 | 1 |
| 29 | Segment 29 | GL | 16 | 1 | Part replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 30 | Segment 30 | GL | 18 | 1 | Part replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
|  |  |  |  | 194.5 |  | 52 | 24 |  | 162 | 191 |
| 2.2.1.1.2 Season- II |  |  |  |  |  |  |  |  |  |  |
| S/n | Indicative Segments | Service | Propsoed dia(inch) | Approx. length, (km) | New/Part/full replacement | No. of Risers to be installed | No. of risers to be removed | MOC for PL & Riser | Indicative Crossing Corrections | Indicative Free Span corrections |
| 31 | Segment 31 | WF | 8 | 4.3 | Full Replacement | 2 | 2 | X-60 CS NACE | 3 | 4 |
| 32 | Segment 32 | WF | 8 | 4.9 | Full Replacement | 0 | 0 | X-60 CS NACE | 8 | 5 |
| 33 | Segment 33 | WF | 10 | 7 | Full Replacement | 2 | 2 | X-60 CS NACE | 21 | 7 |
| 34 | Segment 34 | WF | 10 | 5.1 | Full Replacement | 2 | 2 | X-60 CS NACE | 4 | 5 |
| 35 | Segment 35 | WF | 12 | 6.5 | Full Replacement | 2 | 2 | X-60 CS NACE | 8 | 7 |
| 36 | Segment 36 | WF | 12 | 5.7 | Full Replacement | 0 | 0 | X-60 CS NACE | 8 | 6 |
| 37 | Segment 37 | WF | 12 | 12.2 | Full Replacement | 2 | 2 | X-60 CS NACE | 6 | 12 |
| 38 | Segment 38 | WF | 12 | 2.2 | Full Replacement | 2 | 2 | X-60 CS NACE | 4 | 2 |
| 39 | Segment 39 | WI | 4 | 3.7 | Full Replacement | 2 | 2 | X-52 CS | 2 | 4 |
| 40 | Segment 40 | WI | 6 | 3.9 | Full Replacement | 2 | 2 | X-52 CS | 4 | 4 |
| 41 | Segment 41 | WI | 6 | 1.8 | Full Replacement | 2 | 2 | X-52 CS | 1 | 2 |
| 42 | Segment 42 | PB | 2 | 3.8 | New | 2 | 0 | X-60 CS | 10 | 4 |
| 43 | Segment 43 | WF | 8 | 4.1 | New | 2 | 0 | X-60 CS NACE | 11 | 4 |
| 44 | Segment 44 | WF | 10 | 7 | New | 2 | 0 | X-60 CS NACE | 15 | 7 |
| 45 | Segment 45 | WF | 12 | 4 | New | 2 | 0 | X-60 CS NACE | 9 | 4 |
| 46 | Segment 46 | WF | 12 | 3.8 | New | 2 | 0 | X-60 CS NACE | 13 | 4 |
| 47 | Segment 47 | WF | 14 | 5.5 | New | 2 | 0 | X-60 CS NACE | 7 | 6 |
| 48 | Segment 48 | WF | 14 | 16.4 | New | 2 | 0 | X-60 CS NACE | 7 | 16 |
| 49 | Segment 49 | WF | 16 | 1.5 | New | 2 | 0 | X-60 CS NACE | 15 | 2 |
| 50 | Segment 50 | WF | 16 | 1.5 | New | 2 | 0 | X-60 CS NACE | 14 | 1 |
| 51 | Segment 51 | WF | 18 | 2 | New | 2 | 0 | X-60 CS NACE | 11 | 2 |
| 52 | Segment 52 | GL | 6 | 26.3 | Full replacement | 2 | 2 | X-60 CS NACE | 12 | 26 |
| 53 | Segment 53 | WF | 12 | 16.53 | Full replacement | 2 | 2 | X-60 CS NACE | 9 | 17 |
| 54 | Segment 54 | WF | 16 | 6.53 | Full replacement | 2 | 2 | X-60 CS NACE | 2 | 7 |
| 55 | Segment 55 | WF | 16 | 16.992 | Full Replacement | 2 | 2 | X-60 CS NACE | 27 | 17 |
| 56 | Segment 56 | WF | 16 | 11.8 | Full Replacement | 0 | 0 | X-60 CS NACE | 15 | 12 |
| 57 | Segment 57 | WF | 16 | 11.516 | Full replacement | 2 | 2 | X-60 CS NACE | 1 | 12 |
| 58 | Segment 58 | WF | 16 | 4.237 | Full replacement | 2 | 2 | X-60 CS NACE | 1 | 4 |
|  |  |  |  | 200.8 |  | 50 | 30 |  | 248 | 203 |
| 2.2.1.1.3 Season-III |  |  |  |  |  |  |  |  |  |  |
| S/n | Indicative Segments | Service | Propsoed dia(inch) | Approx. length, (km) | New/Part/full replacement | No. of Risers to be installed | No. of risers to be removed | MOC for PL & Riser | Indicative Crossing Corrections | Indicative Free Span corrections |
| 59 | Segment 59 | GL | 6 | 23 | New | 2 | 0 | X-60 CS NACE | 2 | 23 |
| 60 | Segment 60 | GL | 6 | 16.5 | New | 2 | 0 | X-60 CS NACE | 0 | 17 |
| 61 | Segment 61 | WF | 8 | 7.5 | Full Replacement | 2 | 2 | X-60 CS NACE | 4 | 8 |
| 62 | Segment 62 | GL | 6 | 4.95 | Full Replacement | 2 | 2 | X-60 CS NACE | 5 | 5 |
| 63 | Segment 63 | WF | 12 | 6.3 | Part replacement | 0 | 0 | X-60 CS NACE | 24 | 6 |
| 64 | Segment 64 | WF | 14 | 7.2 | Part replacement | 0 | 0 | X-60 CS NACE | 22 | 7 |
| 65 | Segment 65 | WF | 12 | 7.5 | Part replacement | 0 | 0 | X-60 CS NACE | 4 | 8 |
| 66 | Segment 66 | GL | 4 | 7.5 | New | 2 | 0 | X-60 CS NACE | 4 | 7 |
| 67 | Segment 67 | WF | 18 | 10.6 | Full replacement | 2 | 2 | X-60 CS NACE | 2 | 11 |
| 68 | Segment 68 | WF | 10 | 5.5 | Full replacement | 2 | 2 | X-60 CS NACE | 5 | 5 |
| 69 | Segment 69 | WF | 10 | 3.8 | Full replacement | 2 | 2 | X-60 CS NACE | 5 | 4 |
| 70 | Segment 70 | WF | 12 | 9.95 | Full replacement | 2 | 2 | X-60 CS NACE | 20 | 10 |
| 71 | Segment 71 | WF | 12 | 7.9 | Full replacement | 2 | 2 | X-60 CS NACE | 12 | 8 |
| 72 | Segment 72 | WF | 10 | 9.9 | Full replacement | 2 | 2 | X-60 CS NACE | 10 | 10 |
| 73 | Segment 73 | WF | 12 | 7.3 | Full replacement | 2 | 2 | X-60 CS NACE | 16 | 7 |
| 74 | Segment 74 | WF | 12 | 9.2 | Full replacement | 2 | 2 | X-60 CS NACE | 11 | 9 |
| 75 | Segment 75 | WF | 8 | 4.349 | Full Replacement | 2 | 2 | X-60 CS NACE | 7 | 4 |
| 76 | Segment 76 | WF | 10 | 2.3 | Full replacement | 2 | 2 | X-60 CS NACE | 11 | 2 |
| 77 | Segment 77 | WF | 10 | 9.165 | Full replacement | 2 | 2 | X-60 CS NACE | 28 | 9 |
| 78 | Segment 78 | WF | 12 | 8.415 | Full replacement | 2 | 2 | X-60 CS NACE | 8 | 8 |
| 79 | Segment 79 | WF | 12 | 6.5 | Full replacement | 2 | 2 | X-60 CS NACE | 15 | 6 |
| 80 | Segment 80 | WF | 12 | 6.185 | Full replacement | 0 | 0 | X-60 CS NACE | 14 | 6 |
| 81 | Segment 81 | WF | 12 | 2.266 | Full replacement | 2 | 2 | X-60 CS NACE | 4 | 2 |
| 82 | Segment 82 | WF | 14 | 3 | Full replacement | 0 | 0 | X-60 CS NACE | 8 | 3 |
| 83 | Segment 83 | WF | 14 | 7.6 | Full replacement | 2 | 2 | X-60 CS NACE | 10 | 7 |
| 84 | Segment 84 | GL | 20 | 1 | Part Replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 85 | Segment 85 | GL | 22 | 1 | Part Replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 86 | Segment 86 | GL | 24 | 1 | Part Replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 87 | Segment 87 | WI | 10 | 1 | Part Replacement | 0 | 0 | X-52 CS | 1 | 1 |
| 88 | Segment 88 | WI | 12 | 1 | Part Replacement | 0 | 0 | X-52 CS | 1 | 1 |
| 89 | Segment 89 | WI | 14 | 1 | Part Replacement | 0 | 0 | X-52 CS | 1 | 1 |
|  |  |  |  | 200.4 |  | 40 | 34 |  | 257 | 198 |
| 2.2.1.1.4 Season-IV |  |  |  |  |  |  |  |  |  |  |
| S/n | Indicative Segments | Service | Propsoed dia(inch) | Approx. length, (km) | New/Part/full replacement | No. of Risers to be installed | No. of risers to be removed | MOC for PL & Riser | Indicative Crossing Corrections | Indicative Free Span corrections |
| 90 | Segment 90 | WF | 8 | 4.3 | Full Replacement | 2 | 2 | X-60 CS NACE | 3 | 4 |
| 91 | Segment 91 | WF | 8 | 4.9 | Full Replacement | 0 | 0 | X-60 CS NACE | 8 | 5 |
| 92 | Segment 92 | WF | 10 | 7 | Full Replacement | 2 | 2 | X-60 CS NACE | 21 | 7 |
| 93 | Segment 93 | WF | 10 | 5.1 | Full Replacement | 2 | 2 | X-60 CS NACE | 4 | 5 |
| 94 | Segment 94 | WF | 12 | 6.5 | Full Replacement | 2 | 2 | X-60 CS NACE | 8 | 7 |
| 95 | Segment 95 | WF | 12 | 5.7 | Full Replacement | 0 | 0 | X-60 CS NACE | 8 | 6 |
| 96 | Segment 96 | WF | 12 | 12.2 | Full Replacement | 2 | 2 | X-60 CS NACE | 6 | 12 |
| 97 | Segment 97 | WF | 12 | 2.2 | Full Replacement | 2 | 2 | X-60 CS NACE | 4 | 2 |
| 98 | Segment 98 | WI | 4 | 3.7 | Full Replacement | 2 | 2 | X-52 CS | 2 | 4 |
| 99 | Segment 99 | WI | 6 | 3.9 | Full Replacement | 2 | 2 | X-52 CS | 4 | 4 |
| 100 | Segment 100 | WI | 6 | 1.8 | Full Replacement | 2 | 2 | X-52 CS | 1 | 2 |
| 101 | Segment 101 | WF | 8 | 4.1 | New | 2 | 0 | X-60 CS NACE | 11 | 4 |
| 102 | Segment 102 | WF | 10 | 7 | New | 2 | 0 | X-60 CS NACE | 15 | 7 |
| 103 | Segment 103 | WF | 12 | 4 | New | 2 | 0 | X-60 CS NACE | 9 | 4 |
| 104 | Segment 104 | WF | 12 | 3.8 | New | 2 | 0 | X-60 CS NACE | 13 | 4 |
| 105 | Segment 105 | WF | 14 | 5.5 | New | 2 | 0 | X-60 CS NACE | 7 | 6 |
| 106 | Segment 106 | WF | 14 | 16.4 | New | 2 | 0 | X-60 CS NACE | 7 | 16 |
| 107 | Segment 107 | WF | 16 | 1.5 | New | 2 | 0 | X-60 CS NACE | 15 | 2 |
| 108 | Segment 108 | WF | 16 | 1.5 | New | 2 | 0 | X-60 CS NACE | 14 | 1 |
| 109 | Segment 109 | WF | 18 | 2 | New | 2 | 0 | X-60 CS NACE | 11 | 2 |
| 110 | Segment 110 | GL | 6 | 26.3 | Full replacement | 2 | 2 | X-60 CS NACE | 12 | 26 |
| 111 | Segment 111 | WF | 12 | 16.53 | Full replacement | 2 | 2 | X-60 CS NACE | 9 | 17 |
| 112 | Segment 112 | WF | 16 | 6.53 | Full replacement | 2 | 2 | X-60 CS NACE | 2 | 7 |
| 113 | Segment 113 | WF | 16 | 16.992 | Full replacement | 2 | 2 | X-60 CS NACE | 27 | 17 |
| 114 | Segment 114 | WF | 16 | 11.8 | Full replacement | 0 | 0 | X-60 CS NACE | 15 | 12 |
| 115 | Segment 115 | WF | 16 | 11.516 | Full replacement | 2 | 2 | X-60 CS NACE | 1 | 12 |
| 116 | Segment 116 | WF | 16 | 4.237 | Full replacement | 2 | 2 | X-60 CS NACE | 1 | 4 |
|  |  |  |  | 197 |  | 48 | 30 |  | 238 | 199 |
| 2.2.1.1.5 Season-V |  |  |  |  |  |  |  |  |  |  |
| S/n | Indicative Segments | Service | Propsoed dia(inch) | Approx. length, (km) | New/Part/full replacement | No. of Risers to be installed | No. of risers to be removed | MOC for PL & Riser | Indicative Crossing Corrections | Indicative Free Span corrections |
| 117 | Segment 117 | GL | 6 | 23 | New | 2 | 0 | X-60 CS NACE | 2 | 23 |
| 118 | Segment 118 | GL | 6 | 16.5 | New | 2 | 0 | X-60 CS NACE | 0 | 17 |
| 119 | Segment 119 | WF | 8 | 7.5 | Full Replacement | 2 | 2 | X-60 CS NACE | 4 | 8 |
| 120 | Segment 120 | GL | 6 | 4.95 | Full Replacement | 2 | 2 | X-60 CS NACE | 5 | 5 |
| 121 | Segment 121 | WF | 12 | 6.3 | Part replacement | 0 | 0 | X-60 CS NACE | 24 | 6 |
| 122 | Segment 122 | WF | 14 | 7.2 | Part replacement | 0 | 0 | X-60 CS NACE | 22 | 7 |
| 123 | Segment 123 | WF | 12 | 7.5 | Part replacement | 0 | 0 | X-60 CS NACE | 4 | 8 |
| 124 | Segment 124 | GL | 4 | 7.5 | New | 2 | 0 | X-60 CS NACE | 4 | 7 |
| 125 | Segment 125 | WF | 18 | 10.6 | Full replacement | 2 | 2 | X-60 CS NACE | 2 | 11 |
| 126 | Segment 126 | WF | 10 | 5.5 | Full replacement | 2 | 2 | X-60 CS NACE | 5 | 5 |
| 127 | Segment 127 | WF | 10 | 3.8 | Full replacement | 2 | 2 | X-60 CS NACE | 5 | 4 |
| 128 | Segment 128 | WF | 12 | 9.95 | Full replacement | 2 | 2 | X-60 CS NACE | 20 | 10 |
| 129 | Segment 129 | WF | 12 | 7.9 | Full replacement | 2 | 2 | X-60 CS NACE | 12 | 8 |
| 130 | Segment 130 | WF | 10 | 9.9 | Full replacement | 2 | 2 | X-60 CS NACE | 10 | 10 |
| 131 | Segment 131 | WF | 12 | 7.3 | Full replacement | 2 | 2 | X-60 CS NACE | 16 | 7 |
| 132 | Segment 132 | WF | 12 | 9.2 | Full replacement | 2 | 2 | X-60 CS NACE | 11 | 9 |
| 133 | Segment 133 | WF | 8 | 4.349 | Full replacement | 2 | 2 | X-60 CS NACE | 7 | 4 |
| 134 | Segment 134 | WF | 10 | 2.3 | Full replacement | 2 | 2 | X-60 CS NACE | 11 | 2 |
| 135 | Segment 135 | WF | 10 | 9.165 | Full replacement | 2 | 2 | X-60 CS NACE | 28 | 9 |
| 136 | Segment 136 | WF | 12 | 8.415 | Full replacement | 2 | 2 | X-60 CS NACE | 8 | 8 |
| 137 | Segment 137 | WF | 12 | 6.5 | Full replacements | 2 | 2 | X-60 CS NACE | 15 | 6 |
| 138 | Segment 138 | WF | 12 | 6.185 | Full replacements | 0 | 0 | X-60 CS NACE | 14 | 6 |
| 139 | Segment 139 | WF | 12 | 2.266 | Full replacements | 2 | 2 | X-60 CS NACE | 4 | 2 |
| 140 | Segment 140 | WF | 14 | 3 | Full replacements | 0 | 0 | X-60 CS NACE | 8 | 3 |
| 141 | Segment 141 | WF | 14 | 7.6 | Full Replecement | 2 | 2 | X-60 CS NACE | 10 | 7 |
| 142 | Segment 142 | GL | 20 | 1 | Part Replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 143 | Segment 143 | GL | 22 | 1 | Part Replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 144 | Segment 144 | GL | 24 | 1 | Part Replacement | 0 | 0 | X-60 CS NACE | 1 | 1 |
| 145 | Segment 145 | WI | 10 | 1 | Part Replacement | 0 | 0 | X-52 CS | 1 | 1 |
| 146 | Segment 146 | WI | 12 | 1 | Part Replacement | 0 | 0 | X-52 CS | 1 | 1 |
| 147 | Segment 147 | WI | 14 | 1 | Part Replacement | 0 | 0 | X-52 CS | 1 | 1 |
|  |  |  |  | 200.4 |  | 40 | 34 |  | 257 | 198 |

      - The scope shall include Pre-engineering, Pre-construction/ installation and post installation surveys, detailed engineering, removal and safe disposal of existing riser along with riser clamps (wherever applicable), procurement (except free issue coated line pipes, riser pipes & SPRU), transportation, laying of submarine pipeline, FBE coating at field joints by Robotic Arm Method, use of sleeves at field joints of LE coated pipes, crossing and free span corrections, hook-up, testing and pre-commissioning, etc.

      - Location of proposed risers shall be firmed up based on Pre- engineering Survey. Contractor shall make an effort to locate proposed replacement risers on the same face of Jacket. In case it is not feasible to locate the replacement riser on same face due to space constraint, bidder can suggest during engineering, alternate jacket face to locate risers. This should not constitute any change in scope. In case, riser protector or boat landing exists on the jacket face, where new riser is to be installed, removal & re-installation of riser protector, boat landing along with strengthening complying with the Structural design criteria to make it suitable for Riser protector shall be in the scope of work of the Contractor.

      - Contractor shall design the entire pipeline system in such a way that the piggability of the pipeline system is fully ensured.

      - The respective section of above pipelines and risers for replacement and part replacement are to be laid as per the route firmed up after pre-engineering survey and detailed engineering.

      - Rigid pipeline system shall be provided as per requirements of section-4A. The detailed scope indicating pipeline segments, service and other details are covered in the subsequent sections of the Bid Document.

      - Cathodic protection system shall be as per the FS provided in the bid document.

      - Subsea Tie-in of Pipeline: In case of part-replacement, the subsea tie-in of new pipeline with existing pipeline shall be done through suitable Flange/ end connector arrangement/ Subsea Pipeline Repair Unit (SPRU). Contractor shall be free issued the SPRU for each segment of part replacement. Contractor to prepare the detailed procedure for SPRU installation, which shall be approved by Company. SPRUs shall be installed in subsea Tie-in of each segment of part replacement.

      - Apart from replacement of subsea pipelines/riser, removal and dispose-off of redundant risers (along with two pipe lengths of pipeline with each riser) are under the scope of contractor.

  - DESCRIPTION OF FACILITIES MODIFICATIONS ON EXISTING WELL/PROCESS PLATFORMS

    - GENERAL

- This section of the Bid Document gives description of the basic requirement and criteria for the modifications required for installation of riser. It shall be Contractor’s responsibility to carry out survey, fabricate, transport, install, hook-up, test, pre-commission, start-up & commission including flushing and cleaning of the complete pipeline riser systems and whatever is necessary to take up and carry out the required modifications in shortest possible time in a safe manner. It is an essential requirement that the shutdown of the existing platforms is reduced to absolutely minimum. The Contractor shall be responsible for devising methods and developing detailed procedures to realize this objective and carry out the modifications in an orderly manner without obstructing operations and maintenance of existing facilities. All details and procedures shall be subject to Company’s approval.

- The modification works require cutting, welding, fabrication etc. and other hot works on the existing platforms/ facilities. The Contractor shall obtain hot work permits from the Company prior to taking up any hot work on existing well/ platforms.

- Contractor shall update existing as-built drawings for the intended modifications. Wherever as-built drawings of existing facilities are not available, Contractor shall develop drawings for the intended modifications inclusive of nearby identifiable facilities and update them to an as-built status.

- Contractor shall ensure that the design and modification works shall meet the relevant codes and standards requirements. A typical list of applicable codes is included in this Bid Package. This, however, cannot be taken as an exhaustive list and various codes and standards as mentioned in functional specifications as well as those applicable as per good engineering practices shall also form the basis and shall have to be followed by the Contractor in consultation with Company/ Company’s engineering consultant.

- The Contractor shall be responsible for preparing a detailed procedure for execution of the Modification Works which shall be approved by the Company. The Contractor shall develop and execute the modification works by using prefabricated piping spools, to the maximum extent possible to keep the shutdown of existing well/ process platforms to absolutely minimum. The Contractor shall give at least thirty (30) days’ notice in writing to the Company prior to taking up any Modification Works. The Company reserves the right to alter dates for modifications to meet their production targets and other requirements. The Contractor shall collect the data/ information, if any, from work sites during pre-engineering and pre-construction surveys.

- In case, testing/ pre- commissioning requirement necessitates part inclusion of existing facilities, same shall be considered as included under testing/ commissioning scope of work. All such pre- commissioning activities shall be witnessed by the Company for their satisfactory completion.

      - FLUSHING AND PURGING

- Upon acceptance of the procedures proposed by the Contractor and as per mutually agreed schedule (Refer –Volume 1), the Company will shut down and de-pressurize the affected systems or a part of it, if required, on existing well/ process platforms and hand it over to the Contractor for execution of modification works.

- The Contractor shall be fully responsible for flushing, cleaning and purging of the system including supply of all skillets, gaskets, blinds, chemicals, etc. and making it gas free and whatever required to take up the modification jobs from safety considerations. The Contractor shall make adequate provisions for steaming the hydrocarbon systems for making them oil / gas free.

- The flushing, cleaning and purging operations shall be done under the supervision of the Company’s Representative and procedures and subject to approval by the Company. Supply of the media /fluids required for flushing, cleaning and purging shall be the responsibility of the Contractor. The media / fluids for flushing shall be the conventional media / fluids used for hydrocarbon flushing, cleaning and purging. The flushing medium fluid to be used shall be subject to approval of the Company.

- The Contractor shall develop installation techniques requiring minimum/ partial shutdown of existing well/ process platforms. As far as practicable, the modifications shall be done using the existing flanged connections / spool pieces, if any, spared by the Company, to minimize cutting and welding on the platforms. In case a spool piece is modified for providing hook-up connection, an additional similar size connection along with valve and blind flange shall also be provided. All bolting material and gaskets removed by the Contractor for carrying out modifications and /or hydrostatic testing shall be replaced with new materials supplied by the Contractor as part of his firm scope of work.

- Contractor shall be fully responsible during the entire duration of the execution of the modification for any damage caused to the existing facilities. In case any damage is taken place during the modifications work, the Contractor shall repair or replace the same with new equipment/facilities at no cost to the Company. All such works shall be carried out immediately.

- Any item, which is removed for modification works and not re-used, shall be handed over by the Contractor to the Company on designated supply vessels at offshore as per Company’s instructions. All items requiring re-use shall be re-installed by the Contractor as his firm scope of work.

- Since the existing well/ process platforms are operational, the Contractor shall endeavour to plan and execute his work in such a manner that hot work and existing well/ process platforms’ shut down requirement are kept to the minimum. In any case, the Contractor shall give sufficient notice and obtain prior permission from the Company for hot work or shut down of the existing well/ process platforms. Hot work permits or shutdown may be refused by the Company, if in its opinion the work can be carried out without such needs. The company also reserves its right to make some adjustments in the working time / dates for such hot works / platform shutdown in order to meet its own exigencies.

      - SAFETY STUDY

Contractor shall engage an internationally reputed third party agency having expertise in carrying out CHAZOP, HAZID, HAZOP, SIL study. The workshop shall be convened at the design centre wherein observations/ recommendations shall be deliberated in presence of / with Company’s representatives/ Engineering Consultant/ Vendor the firmed-up recommendations shall be incorporated in relevant documents/drawings and after their approval, P&IDs shall be issued for “Approved for Construction (AFC).

  - CONTRACTOR’S SCOPE OF SUPPLY- Contractor shall be responsible for all other items including consumable except company-supplied coated line pipes, coated risers, and mother pipe for subsea spools and LR Bends, SPRU.

    - The procurement and supply in sequence and at the appropriate time, of all materials (except free issue material i.e., coated line pipes, riser pipes, and mother pipe for subsea spools and LR Bends, SPRU) and consumables required for the completion of work in accordance with the technical specifications/time schedule shall be entirely the responsibility of the Contractor and his quoted price shall include the provision of all such materials. Contractor’s scope of supply shall consist of the following but not limited to:

All materials (subsea flow tee & valves, flanges, fittings, etc.) including operational/maintenance spares.

- Fabrication of subsea tie-in/expansion spools & subsea bends.

- All types of welding consumables, electrodes, filler wires etc.

- All types of structural members as required for pipe supports, temporary supports, scaffolding materials etc.

- Primers and paints as specified in Spec. No. 2005.

- Spool pipes, blinds, plugs, gaskets and other materials/ arrangement required for testing of pipe work. Radiography/ UT/MPI/DP machines and materials as required for NDT.

- Any other material not-specifically mentioned above but required for completeness of the work as per specifications, drawings and instructions of Engineer-in-charge within, scheduled time shall be the Contractor’s responsibility.

    - The procurement of material shall be from Company’s approved Vendor/sub- vendors and necessary documents, test certificates shall be furnished for Company’s review/approval.

    - Transportation of materials to/from Contractor’s/Vendor’s stores/workshop worksite/field for fabrication/installation including handling, loading/unloading etc. included in Contractor’s scope. Transportation of free issue material from company designated location to worksite/field for fabrication/installation including handling, loading/unloading, storage etc. is also included in Contractor’s scope.

    - It shall be the responsibility of the contractor to provide all men and material including Vendor’s representatives for execution of the work and hand over the Pipeline as per the indicated schedule covered elsewhere in the bidding document.

  - QUALITY ASSURANCE

Contractor shall include in his bid the quality assurance plan in line with ISO 9001 (Series) latest edition containing overall quality management procedures, which is required to be adhered to during execution of contract. After the award of the contract, detailed QA plans shall be furnished by the Contractor for the Company’s approval before commencement of execution.

The Contractor shall establish document and maintain an effective quality assurance system as outlined in recognized codes.

Quality assurance system plans/ procedures of the Contractor shall be furnished in the form of a QA manual. This document should cover details of the personnel responsible for the quality assurance, plans/ procedures to be followed for quality control in respect of design, engineering, procurement, fabrication, installation, hook-up and testing. The quality assurance system should indicate organizational approach for quality control and quality assurance of all the activities at all stages of work at site as well as workshop. The QA plan needs to be approved by the Company before the commencement of execution.

The company or its representative shall reserve the right to witness/ inspect, review any or all stages of work at shop or site as deemed necessary for quality assurance.

The Contractor has to ensure adequate deployment of quality control and quality assurance engineer depending upon the quantum of work. The QA/ QC group shall be fully responsible to carry out the work as per contract, bid specification and approved QA/QC plan. In case the engineer in-charge feels that the contractor’s QA/QC engineers are incompetent or insufficient, Contractor has to deploy other experienced engineers as per site requirement and to the full satisfaction of engineer in-charge.

Contractor’s scope includes preparation of welding procedure specification (WPS), procedure qualification records (PQR), Welder Qualification, Pre- qualification of consumable etc., Fabrication of Spool Pieces, Pipe supports, ND testing (UT, DP, MP, RT) including installation, hydro testing, cleaning, flushing, drying, painting, removal of temporary support, scaffolding etc.

  - HEALTH, SAFETY & ENVIORNMENT REQUIREMENTS

The Contractor shall be responsible to comply with code requirements of International Maritime Organization (IMO), International Convention of Safety of life on sea (SOLAS), Occupational Safety & Health Administration (OSHA), ISO - 14000 series, American Petroleum Institute (API) RP-14A, 14B, 14C, 14D, 14E, 14F, 14G, 14H, 14J and the international practices and the requirements as stipulated in Vol.-I of the bid document with regards to Health, Safety & Environment. Besides above, Contractor shall follow International Maritime Contractors Association (IMCA) Guidelines or International code of practice for offshore Diving work. Contractor shall indicate proposed code in bid offer.

During pre-commissioning works & modification works on existing platforms, Contractor shall ensure compliance of various activities related to Safety, Health & Environment as per applicable codes and submit the compliance report to Company. The Contractor shall carry out safety studies as per Functional specification for safety studies no: 5101 and carry out necessary changes wherever required as per the findings of the safety studies. The contractor shall provide as a minimum all operation/safety equipment as per Functional safety specifications No.5102 included in the bid package. Any other works specified elsewhere in the bid package.

Contractor shall develop all the applicable reports as per the requirements of IEC 61511, ISA 84 & IEC 61508. As minimum consolidated report shall include Hazard & Risk Analysis, Allocation of Safety functions to protection layers, SIS safety requirements specification, SIL analysis of SIF (Safety Instrumented Functions). Contractor to note that for the purpose of project scope all Guidelines/ Technical report/ Recommended practices sections of IEC 61511, ISA 84 & IEC 61508 are applicable. List of Safety studies (as applicable) shall include but not be limited to the following:

• Hazard & Operability Study (HAZOP)

• Safety Integrity Level (SIL) Study

• Fire & Explosion Hazard Assessment (FEHA)

• Smoke & Gas Dispersion (SGDA)

• Emergency Systems Survivability Analysis (ESSA)

• Escape, Evacuate & Rescue Analysis (EERA)

• Non-Hydrocarbon Hazard Analysis (NHHA)

• Quantitative Risk Analysis (QRA) & SSIV Study

• CFD Explosion Risk Analysis

• CFD Exhaust Thermal Dispersion Study

• Noise Study

• Acoustic Induced Vibration (AIV) Study

List of PPE to be issued by Contractor: It shall be the sole responsibility of the contractor to provide the following core PPE items to his personnel for all locations and for all jobs before commencement of the work, as per number and frequency specified below:

| S.No. | PPE/Kits and Liveries | Nos. to be issued per person | Frequency of Provision |
| --- | --- | --- | --- |
| 1 | Ready Made Cotton Overall | 2 | Every construction season OR condition-based replacement |
| 2 | Fire Retardant Overall | 2 | Every construction season OR condition-based replacement |
| 3 | Industrial Safety Shoes | 2 pairs | Every construction season OR condition-based replacement |
| 4 | Electrical Safety Shoes (Electrical Hazard rated) | 2 pairs (Electrical Personnel) | Every construction season OR condition-based replacement |
| 5 | Safety Helmet | 2 | Every construction season OR condition-based replacement |
| 6 | Clear Safety Goggles | 2 | Every construction season OR condition-based replacement |
| 7 | Ear Muff | 2 pairs | Every construction season OR condition-based replacement |
| 8 | Hand Gloves (Impact & Cut Resistant) | 4 pairs | Every construction season OR condition-based replacement |
| 9 | Ear Plugs (reusable) | 2 pairs | Every construction season OR condition-based replacement |
| 10 | Hand Gloves (Rubber - Electrical) | 2 pairs | Every construction season OR condition-based replacement |

Note: All PPE shall bear BIS/EN/ANSI marks with valid certification. In addition, work-specific PPE/Kits & Livery items shall also be provided by the Contractor before commencement of work. Contractor shall mandatorily provide ALL additional PPE required as per OISD-STD-155 based on site-specific Hazard Identification & Risk Assessment (HIRA), Job Safety Analysis (JSA), and Permit-to-Work (PTW) requirements during project execution.

  - RESPONSIBILITY OF COMPANY

Company shall make available the pipeline route Corridor survey report, as-built documents, drawings and other relevant information to the extent possible depending upon their availability.

The Company will be responsible for the following:

- Review and approval of documentation as per the document approval matrix

- Provision of relevant Company personnel to attend major project review meetings conducted by the Bidder, including, but not limited to CHAZOP, HAZID, HAZOP’s, SIL, QRA, engineering, design, fabrication, constructability, pre commissioning and Commissioning wherever applicable.

- Procurement of coated line pipes (includes risers) shall be the responsibility of the Company and will be free issued to the contractor, however the engineering inputs will have to be provided by the contractor.

  - RESPONSIBILITY OF CONTRACTOR

The list of Contractor’s responsibility shall include but not be limited to the following:

- All surveys (except Route Corridor Survey) such as pre-engineering, pre-construction, post-construction, as built etc. as described in the bid document.

- Design and detailed engineering of all facilities in accordance with design parameters and International Codes and Standards but incorporating changes/revisions which are not adequately covered and reflected, considering that bid document is solely based on functional specifications.

- Preparation of all fabrication drawings, purchase specifications, specifications and procedures for fabrication, load out tie-down, transportation, offshore installation, hook-up, testing, pre-commissioning and commissioning (wherever applicable) including the existing facilities where modifications are to be carried out or where loose material are to be handed over.

- Procurement (except free issue material) including expediting and inspection of all materials and equipment for construction and incorporation in the facilities. In addition to Company or Company appointed inspection agency, the Contractor has to carry out the inspection of material/equipment through third part inspection agency duly approved by the Company.

- Free issue material (coated line pipe) to be collected from company designated location for further necessary activity. The Contractor shall also be required to ascertain the anode requirements in accordance with the detailed design and its procurement & installation during coating process.

- The procurement of all equipment and material shall preferably be from Company’s approved Vendors /Sub-vendors (Suggested Vendors’ List enclosed). All necessary documents including test certificates shall be furnished for Company’s review and approval.

- Company reserves the right to participate in the selection of vendor for major equipment and items. Vendor, other than those indicated in the suggested vendor list, if proposed then contractor shall notify the company in writing of the name / details of the intended vendor and furnish company with two sets of the vendor’s complete technical bid offer including past experience of supplying similar items and all technical correspondence / clarification furnished by the vendor to the contractor. Contractor shall ensure that the vendor’s technical offer shall be duly vetted by their engineering sub-contractor incorporating observations / recommendations, before submission to the company.

- Company shall have right to hold detail technical discussion with the vendor and visit vendor’s works to satisfy about the vendor’s capability to execute the job. The contractor shall issue the purchase order only after written approval of the company regarding acceptance of the selected vendor. Approval of purchase specifications does not absolve the Contractor from supplying equipment of proven design as per company’s specification, International codes etc requirements.

- Contractor’s scope includes all materials (except free issue material) other than those defined in Company’s scope.

- All types of welding consumables, electrodes, filler wires etc.

- All types of structural members as required for pipe supports, temporary supports, scaffolding materials etc.

- Spool pipes, blinds, plugs, gaskets and other materials/arrangement required for testing of pipe work.

- Radiography/UT/MPI/DP machines and materials as required for NDT as per welding Functional Specifications.

- Any other material not-specifically mentioned above but required for completeness of the work as per specifications, drawings and instructions of Engineer-in-charge within, scheduled time shall be the Contractor’s responsibility.

- Ensuring the effective functionality of cathodic protection systems for submarine pipelines and risers, and if required, executing necessary repairs in accordance with established standards and best practices.

- Load out of all fabricated and bought out components for facilities, coated/wrapped pipelines onto transport barges, sea fastening and transportation to the offshore site in Mumbai High, Neelam & Heera, B&S Fields.

- Field joint coating for FBE- and LE-coated pipes shall be within the Contractor’s scope of work. Field joint coating for FBE-coated pipes in offshore areas shall be carried out using the robotic arm method. The use of sleeves for FBE-coated pipes shall only be permitted in exceptional cases and only after obtaining prior written approval from the Company.

- Laying of OFC cables, piggyback lines, and umbilicals shall also be within the Contractor’s scope of work, along with the installation of I/J tubes.

- Removal/ Relocation/ Reinstallation of existing Jacket anodes, Riser protectors, Boat Landing etc. and any other obstructions on existing platforms wherever encountered to carry out the intended scope of work.

- Offshore installation of all facilities hook-up, testing, pre-commissioning and commissioning (wherever applicable).

- Contractor shall perform leak test of all well platforms as part of pre-commissioning work. Further, Contractor shall pre-commission all hydrocarbons handling system and fire suppression system (wherever applicable). All necessary hook up & pressure reduction provisions for taking hydrocarbons for different systems shall be provided by contractor. All such pre-commissioning activities shall be witnessed by Company for their satisfactory completion.

- It shall be the contractor’s responsibility to prepare project documentation including as built drawings & documents, specifications, operation and maintenance manual, vendor data book etc. In addition to the hard copies, soft copies of all as built drawings on DVD/Portable Hard discs using latest version of software shall be provided. During detailed engineering all drawings and documents shall be generated for submission to the company in hard copy as well as electronic form.

- Contractor shall be required to follow Company’s on-line documentation system (OPMAC) for uploading and online review of documents, drawings etc.

- Instructions for submission of project documentation including as-built (in addition to the hard copy documents) shall be as follows:

Soft copy: - In electronic format using CD/DVD/Portable Hard Discs media.

| Sl. No. | Description | Format |
| --- | --- | --- |
|  | Project Documents | Latest Version of Microsoft Office |
|  | Vendor Drawings, Specifications, Operation & Maintenance Manual, Vendor Data Book etc. (All documents pertaining to packaged items delivered by third party) | Latest Version of PDF |
|  | All Drawings pertaining to modification job (wherein PDS 3D model creation is not envisaged) | Latest Version of AUTOCAD AND/OR MICROSTATION (As per contractor’s convenience) |
|  | All drawings for new platform | Latest Version of MICROSTATION ONLY |

- The entire Project Management should be done by using Microsoft Project Professional management software, considering all the realistic project data, dates and contract stipulated periods of performances. Any other works specified elsewhere in the bid package.

Contractor shall furnish all the information as sought by the company in formats for its data storage and retrieval system at no extra cost to company. The formats shall be provided to the Contractor during detailed engineering/ kick-off meeting.

In accomplishing the above tasks, the Contractor will take total responsibility of executing the project in accordance with this bid document including supply of all materials and consumables, construction equipment, labour etc. and will adhere to bid document instructions and requirements in respect of all matters relating to the project.

The contractor shall ensure that all modifications are designed and carried out such that it will have no adverse effect on existing operations of the platforms.

Reference to basic bid work, design criteria, functional/general specification and drawings need to be made by contractor to follow while executing the work described in project description above.