Special Conditions of Contract for Pipeline Laying Project (PLP)

- Free Issue of Coated Line Pipe and Riser and Mother Pipe for Bends:

  - Company Shall provide Coated line pipes and risers and bends as Free issue Material (FIM). Contractor shall be responsible for inspection of free issue materials at respective manufacturer’s/fabricator’s/Company’s facilities (Within state of Maharashtra/Gujarat, India) along with Company’s representative. Inspection Release Note (IRN) of material shall be jointly signed by representative/TPIs appointed by Contractor and Company.

  - After issue of IRN of respective lot of free issue material, Contractor shall take possession of the material within 15 days from ONGC’s designated yard (Within state of Maharashtra/Gujarat, India) and subsequently arrange for safe handling, transportation of free issue material for laying at Offshore. Delay beyond 15 days may attract demurrage charges levied by manufacturer/Fabricator for keeping/storage of material (if any claims on this account arises) shall be payable by contractor to line pipe manufacturer/fabricator. Subsequent activities such as necessary safe handling, loading, fastening, transportation, and installation and insurance shall be responsibility of the contractor.

1.4 Storage at Jetty during transit to offshore and safe handling of all free issue material shall be responsibility of the contractor.

1.5 Contractor shall maintain an interface register related to all interfaces including free issue material production and supply requirement so that all interface related issues is brought to the notice of Company. Contractor shall attend all interface meetings, along with their sub-contractors if necessary.

1.6	The line segments, along with their respective sizes and lengths as detailed in the A3/ Schedule of Rates (SOR), represent the indicative scope of work considered for evaluation of bids across five seasons. These quantities are used solely for arriving at comparative Price Evaluation during the bidding process. However, the actual scope of work—as identified and finalized by Company shall be communicated to the successful bidder well in advance for the commencement of each seasonal activities along with the priority list of segments. For each season, assured quantity of pipeline segment shall be minimum cumulative length of 160KM for a Construction Season from 16th Oct to 15th May.

Based on schedule of installation of line segment, Contractor shall co-ordinate with Company’s fabricators/facilities regarding fabrication sequence of each free issue item.

1.7 Pipe line route corridor survey of proposed Segments are not envisaged in Pre-Engineering survey scope of Pipe laying contractor. In this regard, route corridor survey shall be provided by Company/ONGC to successful bidder. However, the contractor shall complete all remaining pre-engineering surveys including jacket face survey.

1.8 Contractor shall submit total requirement of line pipe/risers/bends including contingency for free issue segment wise well in advance, however efforts shall be made to keep over all contingencies within 5%. In case during installation, requirement of free issue material exceeds the estimated quantity prior to commence of Offshore activities, contractor shall intimate the same well in advance to ONGC so that necessary process for procurement of additional material can be initiated without affecting the schedule.

1.9 For guarantee and Liability bidder to refer GCC clause No. 6.0 for bidder’s scope of work.

1.10 Refer clause no. 2 below for un-used free issue material.

- Un-used free issue material:

  - Contractor shall be responsible for the safe handling, loading, sea fastening, and transportation of all unused Free issued pipes and risers from the offshore sites to ONGC’s designated yard (Within state of Maharashtra/Gujrat, India). Cargo barges/supply boats for this purpose shall be arranged by the Contractor as part of their scope. A schedule for transportation shall be provided to ONGC in advance to facilitate appropriate arrangements at ONGC’s designated yard.

  - All materials shall be labelled clearly for identification, with accompanying documentation including the material tally, pipe/riser specifications, and certification (if applicable). The material manifest from offshore locations shall be signed and certified by Company representative.

  - Contractor shall be responsible for ensuring proper handover of the materials ONGC’s designated yard to ONGC. ONGC shall issue Delivery Receipt / Challan / Acknowledgment upon receiving the materials. The materials shall be handed over in good condition and as per the packing list submitted by the Contractor.

  - All applicable port charges, regulatory fees, or levies from port authorities shall be borne by the Contractor towards the transportation of Free Issue Material. All necessary clearances for vessel entry at port shall also be the responsibility of the Contractor.

  - Any applicable customs duties or inspections for the unused free issued material shall be managed and borne by ONGC.

- Disposal of Old and Unusable Scrap Material:

  - Contractor shall dismantle the old unserviceable scrap materials (as per Project Scope of Work) in a planned manner so that the work progress on platform is not affected, and barge deck is optimally utilised. Contractor shall make all required arrangements for clearing dismantled materials from the platforms and ensure that the same are not stored on well head platforms and process complexes. Contractor to comply with relevant rules, regulations and HSE requirements.

  - Contractor’s scope with respect to scrap material is demolition / removal, safe handling, loading on cargo barges / supply vessels, sea fastening, transportation from offshore sites to Nhava/Pipavavyard and handing over to ONGC at Nhava/Pipavav yard. Providing of cargo barges / supply boats is within the Contractor’s scope of work. Contractor shall provide schedule of transportation of scrap material to ONGC to enable ONGC to make necessary arrangements at Nhava/Pipavav yard. All the loose scrap material shall be well packed to ensure safe handling and labelled for easy identification at handing over point at Nhava/Pipavav yard. The scrap material manifest from offshore locations shall be signed / certified by Company representative. There shall be official acknowledgement provided by ONGC, in the form of Delivery receipt / challan / acknowledgement.

  - Contractor shall be responsible for safe handling, transportation and handing over of all scrap materials generated during the execution of the project scope of work, at Nhava/Pipavav, within the quoted price.

  - Contractor to make all arrangements for handing over of the scrap at Nhava/Pipavav Jetty. ONGC shall not charge any cost from Contractor for berthing of their vessel for scrap delivery, however any port charges and all other charges as applicable shall be on Contractor’s account which will be as per port authorities.

  - All clearances required to bring the vessel to Nhava/Pipavav jetty will be the Contractor’s responsibility. Unloading and transportation to scrap yard at Nhava/Pipavav will be undertaken by ONGC. Customs charges shall be borne by ONGC.

  - The packaging shall be done in such a way that Single scrap load for one lift should not be more than 10 tonnes and should be of suitable dimension as trailers and shore cranes will be deployed for transportation. Contractor is required to deploy the team of welder and cutter with adequate resources for facilitating the cutting of big size scrap (Over dimensional consignment-ODC). Estimated time of unloading shall be 16-18 hours alongside jetty. No standby charges will be paid to contractor by Company.

- Methodology for additional Scope not covered under Rate Contract (RC):

The methodology for additional Scope not covered under RC proposals / claims submitted by the Contractor shall be evaluated based on Company’s Change order costing methodology. Costs on elements like Project Management, Detailed Engineering, Fabrication, transportation, Installation, Hook Up, Commissioning, Taxes & Duties etc., as applicable, shall be calculated based on Company’s costing methodology as detailed below:

4.1	Additional Scope not covered under RC

| Sl. No. | Cost Component | Methodology |
| --- | --- | --- |
| (i) | Material cost | Based on MTO pertaining to the additional scope shall be verified by TPI/CA / ONGC Rep/ Consultant and Invoices establishing procurement cost of item, duly verified by Company. In case material is delivered ex-works, 4% will be added to arrive at CIF cost. In case of Air freight actual freight cost will be considered based on documentary evidence. |
| (ii) | Survey | The cost of survey shall be based on the actual no. of man days or barge days as applicable, for survey certified by Company / Company authorized representative. The man day rate of engineers shall be as per the rental rate schedule of contract and the barge day rate shall be as per the Contract price schedule. |
| (iii) | Detailed Engineering | The cost of detailed engineering shall be based on the no. of deliverables verified by Company / Company authorized representative and the rates of Engineering deliverables given in the rental rate schedule of contract. In case, due to additional scope, existing engineering documents are required to be revised and no new deliverables are required to be generated, the cost shall be based fixed 20 % of existing deliverable rates given in the rental rate schedule of contract. The no. of deliverables requiring change shall be verified by Company / Company authorized representative. |
| (iv) | Fabrication | 15% of CIF material cost where onshore / offshore fabrication is involved. For offshore fabrication, barge cost shall not be considered. |
| (v) | Offshore transportation (Yard/ Mumbai Port to Offshore) | 1. 15% of CIF material cost in case transported from vendor site to Offshore. 2. In case separate cargo vessel/ supply vessel has been exclusively used for offshore transportation, the cost for transportation shall be worked out based on the offshore deployment of vessel, verified and certified by Company / Company authorized representative and the rate for cargo vessel as per contract. However, before mobilization, Contractor to ensure optimum use of Marine spread deployed with prior intimation to Company and confirmation by Company. |
| (vi) | Offshore installation/ hook-up and commissioning | 1. Wherever marine spread has been used exclusively for additional scope then cost for offshore activities shall be calculated based on the barge days as per DPR duly verified by Company / Company authorized representative on board of barge/ vessel and barge day rate as per the contract for the actual marine spread deployed. However, before mobilization, Contractor to ensure optimum use of Marine spread deployed with prior intimation to Company and confirmation by Company. 2. In case marine support has been used for the work of additional scope along with the other works, number of barge days will be worked out by multiplying the ratio of persons used for the additional scope work divided by total person on board on the day of additional scope executed duly certified by Company / Company authorized representative. The mandays shall be pro-rated as per usage for additional scope work. 3. Where ever marine support is not required, then this component shall be worked out based on man-hours and equipment deployment duly verified by Company / Company authorized representative and considering rental rates and Manhour rates provided in Contract. The consumables shall be verified by Company / Company authorized representative and cost shall be worked out based on purchase orders/Invoices. |
| (vii) | % fee | As per contract provisions. However, % fee shall not be applicable on cost components / items wherever rates are available in the contract |
| (viii) | Taxes and Duties | As per actuals. However input tax credit to be availed by the Contractor and passed on to ONGC. |
| (ix) | Insurance | As per actuals, if Insurance is taken separately for Additional scope work. Payment will be made on reimbursement basis. |
|  | Notes: | There shall be no separate claim towards as built documentation. |

Notes:

- Supporting documents shall be required for all cases except percentage fee.

In case of claims where adequate supporting documents have not been provided, rate reasonability for additional scope claim shall be established with reference as per in house costing methodology, (wherever available/applicable) for additional scope claims.

2. The requirement of marine support for execution of additional scope work shall be indicated at the time of taking ceiling limit approval as per GCC clause 8.1.1.7 of the contract.

3.  Other conditions for additional scope claims shall be as per contract conditions.

- Weather Conditions:

Contractor shall monitor the weather and operate the marine spread within the marine spread specific limiting operational parameters. In case of forecasting/ warning of emergency situations like Cyclonic conditions / Tsunami, Contractor shall communicate about the same to Company along with suitable actions being taken for ensuring safety of ONGC field installations/ facilities and deployed Barge(s)/Vessel(s)/ Manpower by the Contractor under the Contract.

Contractor shall take immediate action and communicate to the sub-contractor(s)/Barge(s)/vessel(s) operating under the contract and ensure that the Barge(s)/Vessel(s) clear out of ONGC fields area and move to safe location at nearby port anchorage and keep Company updated continuously about location of barge(s)/vessel(s) along with safety of manpower till such emergency situation ceases and normal operations are restored. However, Company’s decision in this regard shall be final and binding.

In above situations, Force Majeure clause 7.5 of General Conditions of Contract shall be applicable.

- Audit of Barges/Vessels

6.1 Company will carry out Audit of proposed marine spread before their deployment to field. The indicative check list for the audit is attached at C-9 and C-10. This is in addition to requirements as per clause 10.8 of GCC

6.2 Company will also carry out periodical audits of marine spread deployment at offshore during execution of Project.

- For calculating the no. of days at Appendix A-3 – Price Schedule- VIII. Rental Rate Schedule following is defined:

24 hours will be considered as one equipment day and 12 hours will be considered as one-man day. Further any value less than 24 hours or 12 hours, as applicable, the day will be calculated on pro rata basis.

- In case of conflict / discrepancy / ambiguity with clauses given in the Special Conditions of Contract      (SCC) and General Conditions of Contract (GCC), the clauses of SCC will override those of GCC.

- Payment terms:

The line segments, along with their respective sizes and lengths as detailed in the A3/ Schedule of Rates (SOR), represent the indicative scope of work considered for evaluation of bids across five seasons. These quantities are used solely for comparative assessment during the bidding process. However, the actual scope of work—as identified and finalized by Company shall be communicated to the successful bidders well in advance for the commencement of seasonal activities. Values for Activities will be worked out based on finalized scope of work for each season for making payments as per Milestone Payment Formula A-10 (MPF). Payments for each season will be based on actual work completed as per MPF.

- PERIOD OF CONTRACT:

The Contract shall remain valid for a firm period of five (5) years from the Effective Date (“Contract Period”). Notwithstanding the foregoing, the Company reserves the right to pre‑close or foreclose the Contract any time after completion of a minimum of three (3) seasons. The Company shall provide written notice of its intention to exercise such pre‑closure or foreclosure at least ten (10) months prior to the effective date of termination.

- MOBILISATION:

- CONTRACTOR (successful bidder) shall mobilize and deploy the required Marine spread i.e. pipe-lay barge spread for pipe-laying within 04 Months of NOA or at the commencement of next available Construction season (from 16th of Oct) whichever is later. Contractor shall be given a grace period of 15 days for mobilization without change in minimum assured quantity of 160 kms as indicated in Para 1.6.

Illustration:

Case 1: If mobilization date for the first season works out during ongoing construction season, contractor may mobilize marine spread in the same season upon mutual consent with same terms and conditions. Further, first time mobilization of marine spread may be done earlier than 04 months, upon mutual consent. Minimum assured quantity will be based on prorata basis for the available duration of construction season post mobilization. As brought out above, the said season shall be over and above 5 seasons firm period as envisaged in the tender.

Case 2: If mobilization for the first season works out as 16th Oct, Contractor to deploy required Marine spread i.e. Pipelay barge for commencing pipelaying from 16th Oct.

For subsequent Construction seasons in both the cases above, Contractor shall mobilize and deploy the required Marine spread i.e. pipelay barge for commencing pipelay from  16th Oct.

- If the CONTRACTOR fails to mobilize and deploy the Marine spread i.e. pipelay barge  for  commencing pipelay within the period specified in sub clause (a) above, ONGC shall have, without prejudice to any other right or remedy in law or contract including sub clause (c) below, the right to terminate the contract.

- If the contractor is unable to mobilize / deploy and commence the services within the period specified in sub clause (a) above, it may request ONGC for extension of the time with unconditionally agreeing for levy and recovery of LD.   Upon receipt of such a request, ONGC may at its discretion, extend the period of mobilization and shall recover from the contractor, as an ascertained and agreed Liquidated Damages, a sum equivalent to 1/2 % of respective Season contract value of assured quantity, for each week of delay or part   thereof, subject to a maximum of 10% of respective Season contract value of assured quantity.

- The  parties  agree that the sum specified above is not a penalty but a genuine  pre-estimate  of  the loss/damage which will be suffered by ONGC on account of delay  on the   part of the CONTRACTOR and the said amount will be  payable without proof of actual loss or damage caused by such delay.

- LD will be calculated on the basis of Season contract value of assured quantity excluding duties and taxes, where such duties/taxes have been shown separately in the contract.

- LD on Season wise work: Time is the essence of the contract. If the Contractor is not able to complete &  handover minimum cumulative length of 160KM Pipeline segments in its entirety as per scope in each season (from 16th Oct to 15th May), in such cases, Company can terminate or levy LD on the balance scope of work as below.

If the Contractor fails to complete the entire specified work by the scheduled completion Date (i.e. 15th May for every season) as brought out at GCC clause 6.3.1.1, company may without prejudice to any other right or remedy available to it under the Contract or Law:

i) Recover from the Contractor as ascertained and agreed liquidated damages and not by way of penalty, as under:

In case of delay in completion of assured quantity of work (minimum cumulative length of 160km) in each season, a sum equivalent to ½% (half percent) of balance scope of work of assured quantity during respective Construction Season of the season & ¼%(Quarter percent) of respective balance scope of work of assured quantity during Monsoon period, for each week of delay occurred or part thereof, subject to a maximum of 5% of respective balance scope of work of assured quantity.

However, if contractor has completed certain part of the work within the scheduled completion date and the said part is ready for use and is accepted by ONGC pursuant to GCC clause No.5.10.3, then in that event, Liquidated Damages shall be leviable only on the Contract Price for the balance work remaining incomplete as on the scheduled date of completion.

Note:

•	Notwithstanding the foregoing, the Maximum Liquated Damages for  SCC clauses 12 & 13 shall not exceed 10% of respective Season contract value of assured quantity excluding duties & taxes.

•	For the purpose of calculation of LD, contract price for  each season shall be calculated based on relevant prices at A-3.

•	Common items, if any, not directly identifiable to the above shall be allocated on prorate basis.

AND/OR

ii) Terminate the Contract or a portion or part of the Work thereof. ONGC shall give 14 days notice to the contractor of its intention to terminate the Contract and shall so terminate the contract unless during the 14 days notice period, the Contractor initiates remedial action acceptable to ONGC.

In case the Contractor is unable to complete the assigned work by the schedule completion date, it may request ONGC before expiry of the scheduled completion date, to allow further time for performance of the contract indicating its willingness to pay the LD amount as agreed at (i) above. ONGC may at its discretion allow further time as requested by the Contractor with or without levy of LD.

The parties agree that the amount of LD provided herein is a genuine pre-estimate of the loss/damage which will be suffered on account of delay on the part of the Contractor and the said amount shall be payable on demand without there being any proof of the actual loss or damage caused by such delay/ breach.

- Idling / stand-by charges of Marine Spread: Idle or standby charges for the marine spread due to weather-related delays are not reimbursable, in accordance with GCC Clause 2.3.2.

However, if any vessel—excluding the Transportation Spread as specified in A-3 TABLE-I PART C of the Price Schedule (A-3)—goes on standby for more than 12 consecutive hours due to reasons solely attributable to the Company, idle/standby charges shall be payable. This is also applicable in cases of premature demobilization due to reasons solely attributable to ONGC.

Charges will be calculated based on the applicable Day Rate outlined in A-3 and are capped at a cumulative maximum of 15 days per vessel per season.

- Variation in Quantities: The quantities mentioned in the Price Format are only for evaluation purpose. The actual number and quantity may not be equal to the quantities indicated in the Price Format and the company shall have the right to increase or decrease the quantities of such items during the execution of contract subjected to cumulative assured quantity of 160kms per season.

- SAR (Search and Rescue) related request/ information may be first transmitted to MRCC (Maritime Rescue Coordination Centre) by ships/ vessels/barges/agencies. Further resources deployed by both Company and Contractor for SAR purpose will not be on chargeable basis, by either parties.

- Life Saving Appliances: Contractors should follow OISD standard (OISD-STD-184) regarding the useful life of Life Saving Appliances (LSA) and LSA requirement.

- Joint Delay Analysis (JDA): In order to identify project delays during the project execution and take remedial measures to address these delays, Contractor shall carry out project delay/progress analysis, on quarterly basis and submit the report to Company. The delay/progress analysis report shall cover the following minimum information:

i. 	Project Activities delayed with respect to Scheduled contract dates, with identification of   activities affecting critical path of project.

ii.  	Reasons for the delay

iii. 	Remedial actions required for arresting the delays and to meet project milestone/completion dates.

Activity and time log sheets should be prepared on monthly basis as a part of project scheduling for activities that fall on the critical path of project schedule or likely to fall in critical path. These log sheets shall capture the delay, if any, in completion of activities/tasks and also record the reasons for the delay and to whom (whether ONGC or Contractor) such delay is attributed and need to be signed by ONGC /ONGC authorized representatives and Contractor’s representatives. The above log sheets shall be used while preparing the Joint Statement.

Project Delay Analysis report based on the above joint statement shall be jointly discussed and signed between Company and Contractor.

- E-measurement Book:  The daily progress of work should be recorded by the contractor and submitted in the e-measurement book portal.

- Contractor to comply with ONGC’s Marine Operation Manual with document no. ONGC/ Marine Ops/ Rev-4/ Nov 23 / or any updated / revised version of this document.

- Modalities for providing the K&L / PPEs to contractual workers:

Provisioning

- It shall be the sole responsibility of the contractor to provide the following core PPE items to his personnel before commencement of the work as per frequency specified in SOW:

- Ready Made cotton overall

- Fire retardant overall

- Industrial Safety Shoes

- Safely Helmet

- Clear safety goggles

- Ear muff

- Ear plug (reusable)

- Hand Gloves (for drilling and work-over operation impact resistant gloves to be used) and Work Specific PPE / Kits & Livery items shall also be provided by the contractor before commencement of the Work.

- The Core PPE for contractual workers shall be of same specification (minimum), which are applicable to ONGC employees, except the colour of overall shall be other than orange and preferably maroon with Company's logo / Name of the Company.

- PPE/ KIT CARD shall be maintained for each contract worker in following format:

Safety Items & Kit Card Format

| Sl. No | Particulars |  |  |  | Details/Remarks |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Name of Contractor/Agency/Supplier |  |  |  |  |  |  |
| 2. | Contract Details |  |  |  |  |  |  |
| 3. | Contract Period |  |  |  |  |  |  |
| 4. | No of Contract Labour deployed |  |  |  |  |  |  |
| 5. | Safety items/Kit Card to be issued |  |  |  |  |  |  |
| Sl. No | Name of contract Labour | Kits & Liveries / PPE issued | Date of Issue | Signature of Contract Labour | Signature of Contractor | Verified by PE / Installation Manager | Remarks |
| 1. |  |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |  |

Notes:

    - Safety items/Kits and liveries listed above are indicative and can be modified according to specific work/contract requirement.

    - Technical specifications and norms of the items listed/provided above shall be the same as applicable to regular employees of ONGC, amended or modified from time to time.

    - Queries with regard to PPE/Kits and Liveries shall be referred to ONGC and decision of ONGC in this regard shall be final.

    - An undertaking to be submitted by the Contractor/service provider with the bills that PPE/Kits and Liveries issued in performance of the contract are without any defects and persons deployed complying with safely directives and using the protective equipment’s/clothing as per work requirements.

- The contractor shall be allowed to start the work only after satisfactory outcome of inspection of both registers, i.e the stock register and that maintained for kit cards, which shall be submitted by the contractor alter the placement of NOA.

Monitoring

- Site supervisor of the contractor shall use daily inspection checklists to ensure that all the contractual workers are provided with suitable PPE and the same are being used during the work. During tool box talk, the use of PPE shall be discussed by the contractor supervisors.

- ONGC representative at regular intervals shall jointly check Individual kit cards with Contractor's Supervisor/Safety Officer at site and inspect that necessary PPE / K& L items are being provided and used during the work by contractual personnel.

- Installation Manager / Mines Safety Officer/ HSE Manager shall carry out Surprise checks/ Inspection for verifying the availability of suitable core PPE and its usage by contractual workers. Whenever the contractual workers are found working without any of the core PPEs, Installation Manager shall be empowered to stop the work.

- Undertaking by the contractor with bills raised for supply of Safety items / Kits and liveries: The contractor shall provide in the following annexure an undertaking with the bills raised by him that he has provided requisite PPE/ K&L to personnel deployed in the Contract for the said period:

Format as Annexure to Undertaking

| Name of the Firm/Agency/Contractor: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Nature of Contract |  |  |  |  |  |
| Contract details and validity: |  |  |  |  |  |
| Details of core safety items and other kits and liveries: |  |  |  |  |  |
| Sl. No. | Articles | Quantity | Locations | Date of issue | Remarks |

CERTIFIED THAT:

- I have issued the core safety items and other general kits and liveries to personnel deployed in ONGC, specific to Job/Services as per contract Agreement No.............................

- All the core safety items and other general kits and liveries Items are as per standard BIS/ISO norms and have not outlived its shell life and not in damaged/unusable conditions.

- The safety devices and other appliances provided for the protection or personnel deployed shall be of same standard specification adopted and issued by ONGC.

- In case of any discrepancies or irregularities in complying with safety items/devices, then ONGC is entitled to impose penalty/damages upon services provider, as per contract agreement.

- A standard Safety Kit Card as per contract clause No………. is maintained at site for ready reference and inspection by PE/ONGC representatives/Authorities

Date:		(Signature & Seal of the Contractor)

Place:

Actions In case of Non-Compliance:

- A list of PPE items issued by the contractor to the contractual Workers is to be submitted by the contractor to ONGC before commencement of work along with relevant supporting documents related to PPEs provided by the contractor. The same shall be verified by ONGC before giving clearance to start the work. In case the PPEs are not provided by the contractor before the commencement of work, mobilization by the contractor will be considered as incomplete and the LD wherever applicable as per prevailing terms of contract will be imposed.

- Whenever the contractual workers are found working without any of the core PPEs, installation Manager shall be empowered to stop the work as below.

- Ask the defaulting worker to leave the site and mark him absent;

- Penalty will be Imposed on contractor at the rate of Rs1000/- per person per day for non-use of any of the PPE Items by the contractual personnel:

- If the contractor fails to provide suitable replacement of damaged/ unsuitable PPEs to his personnel, contractor shall be asked to stop the work immediately till corrective actions are taken. In such a scenario the completion date of the job will not be extended and ONGC shall not make any payment till the work is kept in suspension due to non-use of PPEs.

- In case of repeated violation of non-use of PPEs by the contractual workers for more than three times in onshore operations, the Contractor will permanently remove the defaulters from the site and replace them without delay and at no extra cost to ONGC. Likewise. In case of offshore operations, for repeated violations of non-use of PPEs by the contractual workers for more than three times, ONGC shall ask the concerned contractor to send the defaulters back to base at his own expenses and suitable replacement will be provided without delay and at no extra cost to ONGC.

In any extreme case, if Contractor has failed to start work on the due date only because of non-provision of PPE. ONGC shall review the requirement and on its sole discretion decide to agree to the Contractor request for Issuing PPE to its personnel on cost basis or otherwise. Contractor shall be bound by ONGC decision.