## WSSRP-2
Appendix A-10 Milestone Payment Formula Sump Cassion and SWLP Casing Replacement Project (S&SRP) |  |  |  |  | PART – III
APPENDIX A-10
Sl. No. | Activity | Weightage | Milestone % | Milestone for Payment | Payment to the Contractor
[5 empty] | Member 1-% | Member 2-%
| (A) | (B) | (D) | (E) | Consortium Member (1) | Consortium Member (2)
1 | INSURANCE
1.1 | Insurance | 0.87% of I.A | 85 | a) Upon submission of certificate of insurance (Cover Note) for insurance policy(s) specific for the project and its acceptance by Company in terms of clause 7.3.13.1.(a),(b)&(c) of GCC and proof of 100% premium paid to Insurance Company. | X | X
|  |  | 15 | b) Upon submission of insurance policy(s) specific for the project and its acceptance by Company in terms of clause 7.3 of GCC. | X | X
2 | SURVEY
2.1 | Pre-Engineering / Pre-Installation / Post Installation Survey | 0.92% of I.A | 40 | a) Upon completion of pre-engineering survey and submission of complete survey report and its acceptance by Company. | X | X
|  |  | 20 | b) Upon completion of pre-installation survey and submission of complete survey report and its acceptance by Company. | X | X
|  |  | 40 | c) Upon completion of post- installation survey and submission of complete survey report and its acceptance by Company. | X | X
3 | DESIGN AND ENGINEERING
3.1 | Design Engineering | 3.89% of I.A | 100 | a) Upon progressive completion of engineering as approved and certified by Company. | X | X
4 | PROCUREMENT OF MATERIAL
4.1 | Procurement of Materials | 16.44% of I.A | 5 | a) Upon progressive placement of LOI / PO and Acceptance by vendor. | X | X
|  |  | 30 | b) Upon progressive dispatch from vendor works and submission of supporting documents thereof. | X | X
|  |  | 30 | c) Upon progressive arrival at fabrication yard, submission of mill inspection and test reports, verification of receipt of material by TPI/CA. | X | X
|  |  | 30 | d) Upon progressive completion of sail out of items/equipment. | X | X
|  |  | 5 | e) Upon clearance of Punch point related to the above milestones, if any | X | X
5 | FABRICATION - STRUCTURAL & NON-STRUCTURAL
5.1 | Fabrication - Strcutrual and Non-structural | 4.24% of I.A | 85 | a) Upon progressive completion of fabrication as certified by Company. | X | X
|  |  | 10 | b) Upon progressive completion of respective sail out of items/equipment from Yard. | X | X
|  |  | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any. | X | X
6
6.1 | Installation | 41.78% of I.A | 5 | a) Upon progressive arrival of materials at offshore | X | X
|  |  | 85 | b) Upon progressive completion of installation / modification of item /equipment /system. | X | X
|  |  | 10 | c) Upon completion of punch points, if any. | X | X
7 | Hook-Up with existing facilities/Testing/Pre- Commissioning and Commissioning (wherever applicable and as per scope of work)
7.1 | Hook-Up with existing facilities/Testing/Pre- Commissioning and Commissioning (wherever applicable and as per scope of work) | 27.86% of I.A | 80 | a) Upon progressive completion of Hook-up, testing, pre-commissioning / commissioning work of each Equipment /item / systems.(Including all electrical, Instrumentation, structural & piping etc.) | X | X
|  |  | 10 | b) Upon progressive submission of commisioning test reports & its acceptance for by Company (ONGC). | X | X
|  |  | 10 | c) Upon submission of Certificate of Approval for the respective facility (item/equipment/system wise) from Certification Agency / Company. | X | X
8 | Liquidation of punch points
8.1 | Liquidation of punch points | 2.00% of I.A. | 100 | Upon completion of Punch Points related to Hookup, Pre-commissioning, commissioning activity, if any | X | X
9 | AS-BUILT DOCUMENTATION
9.1 | As Built for work to be completed in the scope of LSTK Contractor | 2.00% of I.A. | 100 | Upon submission of As-built drawing, documents, Software Files (as applicable) , Vendor dossiers, Operation & Maintenance Manuals etc. for the Project Scope and acceptance by Company as per GCC 5.1.9.3. | X | X
10 | Customs Duty | 100% of I.B. of Appendix A3 | 100 | Reimbursement at actual limited to the amount indicated herein on submission of documentary proof viz. bill of entry in original duly addressed by the Custom Authority and the amount of duty paid thereof along with relevant supporting documents subject however to provisions of change in law as per clause 7.6 (subsequent legislation) of GCC. | X | X
11 | Goods and Service Tax | 100% of I.C. of Appendix A3 | 100 | Payable at actual, limited to the amount indicated herein, along with relevant milestone as per invoice under Goods and Service Tax rules subject howev-er to provisions of change in law as per clause no. 7.6 (Sub-sequent legislation) of GCC. | X | X
General Notes
1 | Taxes and duties shall be paid in INR only.
2 | The requirement of dispatch / sail out wherever referred shall be the "Bill of Lading" for dispatch (as applicable) and certificate of carrier for sail out (as applicable).
3 | All yard and offshore related activities to be inspected and certified by Certification Agency / Third Party Inspection Agency.
4 | Release notes shall be issued by Certification Agency.
5 | Milestone to be submitted platform wise / items /equipment-wise.