## Milestone Payment Formula
A-10-Project : Pipeline Replacement Project X (PRP-X)
Ref | Activity | Weightage | Amount of Col. B in Quoted Currency | Milestone % | Milestone % | Milestone for Payment | Milestone Amount in USD
| (A) | (B) | (C ) | (D) |  | (E) | (F)
1 | INSURANCE
1.1 | Insurance | 3.11 % of I.A. | 0 | 85 | 85 | a) Upon submission of certificate of insurance (Cover Note) for insurance policy(s) specific for the project and its acceptance by Company in terms of clause 7.3.13.1.(a),(b)&(c) of GCC and proof of 100% premium paid to Insurance Company.
|  |  |  | 15 | 15 | b) Upon submission of insurance policy(s) specific for the project and its acceptance by Company in terms of clause 7.3 of GCC. |  | 3.11
2 | SURVEY
2.1 | Submarine Pipelines and Risers | 92.89% of S.SURP of Table II-A3 | 0 | 40 | 40* | a) Upon completion of pre-engineering survey and submission of complete survey report and its acceptance by Company.
|  |  |  | 20 | 20 | b) Upon completion of pre-installation survey and submission of complete survey report and its acceptance by Company.
|  |  |  | 40 | 40 | c) Upon completion of post- installation survey and submission of complete survey report and its acceptance by Company.
*For pipeline segments, data of Pipeline route corridor survey will be shared by company and payment towards milestone no.2.1(a) shall be made along with milestone no.2.1(b).
2.2 | Topside modification | 92.89% of S.SURT of Table II-A3 | 0 | 40 | 40 | a) Upon completion of pre-engineering survey and submission of complete survey report and its acceptance by Company.
|  |  |  | 20 | 20 | b) Upon completion of pre-installation survey and submission of complete survey report and its acceptance by Company.
|  |  |  | 40 | 40 | c) Upon completion of post- installation survey and submission of complete survey report and its acceptance by Company.
3 | DESIGN AND ENGINEERING
3.1 | Submarine Pipelines and Risers | 92.89% of S.DESP of Table II-A3 | 0 | 100 | 100 | a) Upon progressive completion of engineering as approved and certified by Company.
3.2 | Topside modification | 92.89% of S.DEST of Table II-A3 | 0 | 100 | 100 | a) Upon progressive completion of engineering as approved and certified by Company.
4 | PROCUREMENT OF MATERIAL - STRUCTURAL
Note: Basis of milestone achievement shall be as per MTOs which are good to order. Total tonnage shall be obtained during design engineering.
4.1 | Platforms Modification-Deck Extension/ modification | 34 % of 92.89% of S.DECK of Table II-A3 | 0 | 5 | 5 | a) Upon progressive placement of PO and Acceptance by vendor.
|  |  |  | 20 | 20 | b) Upon progressive dispatch from vendor works and submission of supporting documents thereof.
|  |  |  | 40 | 40 | c) Upon progressive arrival at fabrication yard, submission of mill inspection and test reports, verification of receipt of material by TPI/CA.
|  |  |  | 20 | 20 | d) Upon progressive completion of fabrication as certified by Company
|  |  |  | 10 | 10 | e) Upon completion of respective sail out
|  |  |  | 5 | 5 | f) Upon clearance of Punch point related to the above milestones, if any
5 | PROCUREMENT OF EQUIPMENT & MATERIALS - EXCLUDING STRUCTURAL
5.1 | Topside modification | 74 % of 92.89% of M.TOP of Table II-A3 | 0 | 5 | 5 * | a) Upon progressive placement of LOI and acceptance by vendor.
|  |  |  | 5 | 10 * | b1). 5% Upon progressive approval of prelim Purchase Specifications at 1st Stage, for PS items, as applicable. #
|  |  |  | 5 |  | b2). 5% Upon progressive approval of final Purchase Specification at 2nd Stage, for PS items, as applicable. #
|  |  |  | 60 | 60 | c) Upon progressive dispatch from vendor works and submission of inspection & dispatch documents.
|  |  |  | 20 | 20 | d) Upon progressive arrival at fabrication yard/site submission of material test certificates and test reports, verification by TPI/CA and acceptance by Company.
|  |  |  | 5 | 5 | e) Upon progressive submission of release note of Certification Agency and clearance of punch points related to the above procurement milestones, if any
5.2 | Material –Coating-CP System | 30 % of(92.89%) of S.PIPE of Table II-A3 | 100 | 5 | 5 * | a) Upon progressive placement of LOI and acceptance by vendor.
|  |  |  | 5 | 10 * | b1). 5% Upon progressive approval of prelim Purchase Specifications at 1st Stage, for PS items, as applicable. #
|  |  |  | 5 |  | b2). 5% Upon progressive approval of final Purchase Specification at 2nd Stage, for PS items, as applicable. #
|  |  |  | 60 | 60 | c) Upon progressive dispatch from vendor works and submission of inspection & dispatch documents.
|  |  |  | 20 | 20 | d) Upon progressive arrival at fabrication yard/site submission of material test certificates and test reports, verification by TPI/CA and acceptance by Company.
|  |  |  | 5 | 5 | e) Upon progressive submission of release note of Certification Agency and clearance of punch points related to the above procurement milestones, if any
5.3 | SPRU | 18 % of 92.89% of S.SPRU of Table II-A3 | 0 | 5 | 5 * | a) Upon progressive placement of LOI and acceptance by vendor.
|  |  |  | 5 | 10 * | b1). 5% Upon progressive approval of prelim Purchase Specifications at 1st Stage, for PS items, as applicable. #
|  |  |  | 5 |  | b2). 5% Upon progressive approval of final Purchase Specification at 2nd Stage, for PS items, as applicable. #
|  |  |  | 60 | 60 | c) Upon progressive dispatch from vendor works and submission of inspection & dispatch documents.
|  |  |  | 20 | 20 | d) Upon progressive arrival at fabrication yard/site submission of material test certificates and test reports, verification by TPI/CA and acceptance by Company.
|  |  |  | 5 | 5 | e) Upon progressive submission of release note of Certification Agency and clearance of punch points related to the above procurement milestones, if any
5.4 | Procurement of material for Hot Tapping (S.HOTT) for Hot Tapping Job (subsea split tee, valves, etc.) | 18 % of 92.89% of S.HOTT of Table II-A3 | 0 | 5 | 5 * | a) Upon progressive placement of LOI and acceptance by vendor.
|  |  |  | 5 | 10 * | b1). 5% Upon progressive approval of prelim Purchase Specifications at 1st Stage, for PS items, as applicable. #
|  |  |  | 5 |  | b2). 5% Upon progressive approval of final Purchase Specification at 2nd Stage, for PS items, as applicable. #
|  |  |  | 60 | 60 | c) Upon progressive dispatch from vendor works and submission of inspection & dispatch documents.
|  |  |  | 20 | 20 | d) Upon progressive arrival at fabrication yard/site submission of material test certificates and test reports, verification by TPI/CA and acceptance by Company.
|  |  |  | 5 | 5 | e) Upon progressive submission of release note of Certification Agency and clearance of punch points related to the above procurement milestones, if any
5.5 | Procurement of material for crossings, (milestone will be paid after completion of all crossings of each segment) | 20 % of 92.89% of S.CROSS of Table II-A3 | 0 | 85 | 85 | a) Procurement of Crossings Materials and arrival at yard/offshore
|  |  |  | 15 | 15 | b) Completion of procurement related punch points.
5.6 | Procurement of material for freespan (milestone will be paid after completion of all freespan of each segment) | 20% of 92.89% of S.FREE of Table II-A3 | 0 | 85 | 85 | a) Procurement of Freespan Material and arrival at yard/offshore
|  |  |  | 15 | 15 | b) Completion of procurement related punch points.
Note:-
* Applicable where the selected vendor is from ONGC’s vendor list or where PQD has already been approved by ONGC before placement of LOI. For others, where PQD is not approved before LOI, payment against milestones a & b above (i.e placement of LOI & upon approval of PS) will be issued together and Contractor will get 15% on completion of milestone ‘a’ and ‘b’ together.
# For non-PS-items, 10% above (b1 & b2) shall be clubbed with dispatch of material milestone (c)
1) Basis for milestone achievement for Sl. No. 5.1 to 5.3 shall be as per PS/MTO quantity for order placement per pipeline segment scope of work, this shall be based on design and engineering.
6 | FABRICATION - STRUCTURAL & NON-STRUCTURAL
6.1 | Anticorrosion, Weight Coating including installation of Anodes of Pipelines, risers etc. | 65 % of (92.89%) of S.PIPE of Table II-A3 | 0 | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
6.2 | Riser and riser bends and riser clamps (weight factor: Riser 85% ; Riser Bends 10%, riser clamps 5% ) | 5 % of (92.89%) of S.PIPE of Table II-A3 | 0 | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
6.3 | Modification of platforms (non-structural) | 26 % of 92.89% of M.TOP of Table II-A3 | 0 | 85 | 85 | a) Upon progressive completion of fabrication as certified by Company.
|  |  |  | 10 | 10 | b) Upon completion of respective sail out.
|  |  |  | 5 | 5 | c) Upon completion of punch point related to the above fabrication milestones, if any.
7 | INSTALLATION
7.1(a) | Modification of platforms(a) | 50 % of 92.89% of S.IPHT of Table II-A3 | 0 | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of installation/modification of each platform.
|  |  |  | 10 | 10 | c) Upon completion of punch points, if any.
7.1(b) | Platforms Modification-Deck Extension/ modification(b) | 66 % of 92.89% of S.DECK of Table II-A3 | 0 | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of installation/modification of deck of each platform.
|  |  |  | 10 | 10 | c) Upon adjustments of variations and completion of punchpoints if any, of deck extension
7.2 | Submarine Pipelines | 92.89% of S.INSP of Table II-A3 | 0 | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of installation/ laying of each pipeline segment.
|  |  |  | 10 | 10 | c) Upon adjustments of variations and completion of punchpoints if any, of each pipeline segment /respective item.
7.3 | Installation of risers, riser bends, riser clamps, sub-sea tie-in spools etc. (weight factor: Riser 85% ; Riser Bends 10%, riser clamps & sub-sea tie-in spools etc 5% ) | 92.89% of S.INSRI of Table II-A3 | 0 | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon progressive completion of riser and I/J Tube installation and spool tie in.
|  |  |  | 10 | 10 | c) Upon submission of release note by certification agency and completion of punch points related to Installation, if any.
7.4 | Demolition of riser plus two pipe-lengths from sea bed | 92.89% of S.DEMR of Table II-A3 | 0 | 90 | 90 | a) Upon demolition of riser and two pipe-lengths
|  |  |  | 10 | 10 | b) Upon submission of proof of receipt for demolished material at NHAVA and completion of punch points.
7.5 | Demolition of topside facilities (excluding NM) | 92.89% of S.DEMT of Table II-A3 | 0 | 90 | 90 | a) Upon demolition of topside facility
|  |  |  | 10 | 10 | b) Upon submission of proof of receipt for demolished material at NHAVA and completion of punch points.
7.6 | Installation of crossings, (milestone will be paid after completion of all crossings of each segment) | 80% of 92.89% of S.CROSS of Table II-A3 | 0 | 85 | 85 | a) Progressive payment segmentwise upon Installation of crossings
|  |  |  | 15 | 15 | b) Upon adjustments of variations and completion of punch points if any, of each pipeline segment /respective item
7.7 | Installation of freespan (milestone will be paid after completion of all freespan of each segment) | 80 % of 92.89% of S.FREE of Table II-A3 | 0 | 85 | 85 | a) Progressive payment segmentwise upon Installation of freespan.
|  |  |  | 15 | 15 | b) Upon adjustments of variations and completion of punchpoints if any, of each pipeline segment /respective item
7.8 | Installation of SPRUs (as applicable) | 82 % of 92.89% of S.SPRU of Table II-A3 | 0 | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of installation on each pipeline segment
|  |  |  | 10 | 10 | c) Upon completion of punch points, if any
7.9 | Hot Tapping Job (S.HOTT) | 82 % of 92.89% of (S.HOTT of Table II-A3 | 0 | 5 | 5 | a) Upon arrival of materials at offshore
|  |  |  | 85 | 85 | b) Upon completion of Hot Tapping Job and hook-up with pipeline segment
|  |  |  | 10 | 10 | c) Upon completion of punch points, if any
7.1 | Flush Burial (milestone will be paid after completion of of each segment) | 92.89% of S.FLBU of Table II-A3 | 0 | 85 | 85 | a) Progressive payment upon segmentwise Completion of Flush Burial.
|  |  |  | 15 | 15 | b) Upon adjustments of variations and completion of punchpoints if any, of each pipeline segment /respective item
Note: 1. Basis of milestone achievement shall be per segment for pipelines, per demolition of riser and of riser protector with associated topside facilities. Milestones 7.1(c ), 7.4(b) and 7.5(b) to be raised after completion of all these activities of each pipeline.
8 | Hook-Up with existing facilities/Testing/Pre- Commissioning and Commissioning (wherever applicable and as per scope of work)
8.1 | Submarine Pipelines | 92.89% of S.HPIPE of Table II-A3 | 0 | 80 | 80 | a) Upon completion of Hook-up, testing, pre-commissioning work of each segment
|  |  |  | 10 | 10 | b) Upon submission of test reports & its acceptance by Company
|  |  |  | 10 | 10 | c) Upon submission of Certificate of Approval for the respective facility from Certification Agency
8.2 | Topside modification | 50% of 92.89% of S.IPHT of Table II-A3 | 0 | 90 | 90 | a) Upon completion of work on each platform
|  |  |  | 10 | 10 | b) Upon submission of test reports & its acceptance by Company and completion of punch points, if any
9 | Liquidation of punch points
9.1 | Liquidation of punch points | 2.00% of I.A. | 0 | 100 | 100 | Upon completion of Punch Points related to Hookup, Pre-commissioning, commissioning activity, if any
10 | AS-BUILT DOCUMENTATION
10.1 | As Built for work to be completed in the scope of LSTK Contractor | 2.00% of I.A. | 0 | 100 | 100 | Payment upon submission of As-built drawing, documents, Software Files (as applicable) , Vendor dossiers, Operation & Maintenance Manuals etc. for the respective line segment in the project Scope and acceptance by Company as per GCC 5.1.9.3.
11 | Customs Duty | 100% of I.B. of Appendix A3 | 0 | 100 | 100 | Reimbursement at actual limited to the amount indicated herein on submission of documentary proof viz. bill of entry in original duly addressed by the Custom Authority and the amount of duty paid thereof along with relevant supporting documents subject however to provisions of change in law as per clause 7.6 (subsequent legislation) of GCC.
12 | Goods and Service Tax | 100% of I.C. of Appendix A3 | 0 | 100 | 100 | Payable at actual, limited to the amount indicated herein, along with relevant milestone as per invoice under Goods and Service Tax rules subject however to provisions of change in law as per clause no. 7.6 (Sub-sequent legislation) of GCC.
11 | Mob-Demob
11.1 | Mob | 50% of 92.89% of I.A.(ii) | 0 | 100 | 100 | For first mobilization, after getting all statutory clearances when PLB move for offshore operation to start pipe-lay work.
11.2 | Demob | 50% of 92.89% of I.A.(ii) | 0 | 100 | 100 | When the PLB has been demobilized from offshore at the completion of the contract scope.
|  | Total | 100 |  |  |  | 0
General Notes
1 | Taxes and duties shall be paid in INR only.
2 | The requirement of dispatch / sail out wherever referred shall be the "Bill of Lading" for dispatch (as applicable) and certificate of carrier for sail out (as applicable).
3 | All yard and offshore related activities to be inspected and certified by Certification Agency / Third Party Inspection Agency.
4 | Release notes shall be issued by Certification Agency.
5 | Milestone to be submitted platform wise, pipeline segment wise and riser wise.
6 | Payment of transportation of pipelines and installation of pipeline with / without Robotic arm will be done together.