GOVERNMENT OF ASSAM PUBLIC WORKS (B & NH) DEPARTMENT

(Building)

EPC CONTRACT

Name of Work:

“Construction of Judicial Guest House at Kaziranga, Assam”

# SPECIAL CONDITIONS OF CONTRACT (SCC)

- No extension of time will be considered for delayed payment; if any from the Department.

- Time for completion – 18 Months

- Bidders are required to complete the work as per milestone mentioned in Annexure F.

Non completion of work of a particular component shall attract levy of LD/compensation in the same. The bidders will suitably plan and steer the processes, so that the construction activities could progress faster, so as to facilitate building's completion in a phased manner.

- Payment schedule as provided in NIT is at macro level worked out based on budget head. Successfully bidders has to submit micro level payment schedule after completion of Detail Engineering with proper supporting documents before first running bill without disturbing the percentage weightage of each category. Chief Engineer PWD (Building) Assam will be approving authority with due approval of engineer in charge.

- It's prerogative of client to get executed excluded items from contractor through specialized agency under extra item clause as per norms after due sanction and approval from. Government/ competent authority or by inviting separate call of tender.

- The contractor has to ensure that all the manufacturers/ authorised service provider/vendors/ suppliers of the Electromechanical equipment should provide warranty/ guarantee as mentioned in document. Comprehensive Maintenance will run concurrently with DLP.

- For smooth transition, Separate agreement for each electromechanical equipment/ services for comprehensive operation and maintenance will be transferred from Assam PWD (Building)/ Client or Client nominated operation & maintenance supervising agency with respective manufacturers/ authorised service provider/ vendors/ specialised agency of civil/ Electromechanical equipment for requisite period.

- During construction as mentioned above fencing of the building shall be done with 12meter High barricading or as per NGT norms stringent of both will be applicable to separate the building under construction works with Completed building as well as outer periphery and boundary wall. The barricading of 12‐meter height along from road side and outer boundary the periphery of the project site shall be constructed by contractor as per direction by Engineer‐in‐ charge. The barricading constructed and shall be aesthetically maintained by regular cleaning and painting by the contractor as directed by the Engineer‐ in‐ charge. The expenditure Incurred for barricading and maintenance of barricading shall be borne by the contractor.

- The Contractor is required to use standard software like MS project, Primavera, etc. for project management, ensuring successful commissioning of project. Bidder will also implement contract management and project management through standard mutually agreed software etc. and will also provide customized dashboard in format approved by Assam PWD (Building) for facilitating project monitoring including providing qualified manpower for updating the dashboard

- The Design, Engineering, Procurement and Construction (EPC) of RCC Framed Structure building including civil works, external & internal electrical works, external & internal plumbing works,

External development etc. as per scope of work and tender documents including preparation of coordinated drawings for all services and make all necessary co‐ordination for satisfactory execution of all works/activities in time bound manner. Develop various 3 D views and model of the buildings.

The efforts will be made by the Assam PWD (Building) to handover the site to the Contractor free of encumbrances. However, in case of any delay in handing over of the site to the Contractor by the Client then Assam PWD (Building) shall only consider suitable extension of time for the execution of the work. It should be clearly understood that the contractor will not be entitled for any extra claim on such account and Assam PWD (Building) shall not consider any revision in contract price or any other compensation whatsoever. The contractor shall be responsible to obtain all statuary approval (Pre & Post Construction) for commencement of work from all statuary authority/Departments.

- The Detailed Scope of works shall be as elaborated in the detailed Design Basis Reports (DBR’s), Technical Specifications, Tender Drawings, Payment Schedule, Finishing Schedule, BOQ Preamble and conditions elaborated in this tender document. The scope of works shall include:

  - The concept Plan shall be provided by Assam PWD (Building) to the contractor. The Contractor shall design and prepare detailed working drawings for all works like Architecture, Finishing, Structural and services design eg. Electrical, Plumbing, External development etc. The contractor shall prepare all coordinated drawings for all services and make all necessary co‐ordination for satisfactory execution of all works/activities in time bound manner. Develop various 3 D views and model of the buildings.

  - Defects liability period shall be 12 months after declaring the original construction work complete by the competent authority.

  - A model, 3D view and walkthrough will be prepared & presented to Assam PWD (Building)& Client within 15 days from award of work as per conceptual plan released by Assam PWD (Building). The latest software of design engineering Including STAADPRO, AutoCAD, Revit etc. will be used for design & Engg. Purpose. All softcopies shall be made available to Assam PWD (Building)/PMC Consultant appointed by Assam PWD (Building) as required.

  - The soil investigation report will be provided by Assam PWD (Building) to Contractor for reference purpose only. However, they are required to get it done independently to satisfy themselves as per design requirements.

  - Any changes as per requirement of Client/Assam PWD (Building) will be done by agency with no any extra charge and time overrun.

  - Structural design vetted by IIT/NIT/Govt. College approved by Assam PWD (Building) and all the drawings and plan has to be get approved from Assam PWD (Building)/PMC Consultant appointed by Assam PWD (Building) before execution,

  - The contractor will get all structural design and drawings vetting from any of IIT Guwahati or any other premier institutions approved by Assam PWD (Building)and cost for the same will be borne by Contractor.

  - The contractor shall at their own conduct topographical survey and geotechnical investigation, Hydrological survey etc. from specialized agencies.

  - C & D waste generated at site to be properly done as per norms at authorized recycling plant of municipal body.

  - If Treated water of STP is available nearby, contractor to make suitable arrangements for use of water in construction and ground water utilization to be avoided.

  - Landscaping work and road network to be taken up parallel to building work and should be completed within time limits as stipulated.

  - The activities to be carried out for the completion of the Project shall include the following and any additional activities incidental to these:

    - Buildings and all services design and execution as specified.

    - Getting all statutory approvals / permissions / planning permits of the statutory / local / governmental agencies as required incidental to Pre‐construction, Construction and completion.

    - Submission of the completion (i.e. ‘as‐built’) drawings and other related documents, both a hard copy and the soft copy in Auto CAD or any other IT application used for the purpose.

    - Preparation of specifications and vendor list (in case not already provided) for all equipment wherever necessary and called upon to do so and getting these approved from Assam PWD (Building).

    - Obtaining occupancy certificate and related NOC’s from statutory/ local/governmental agencies. Statutory payment on this account will be reimbursed by the client at actual on submission of proof of deposition.

    - Executing the work in a befitting manner to obtain GRIHA Certification (minimum 3 Star rating) for the building including engaging a experienced Consultant to assist the Contractor in obtaining the rating. License/Application fee, if any, shall be reimbursed by the Consultant to the Contractor on actuals.

All expenditure of above deemed to be included in the tender cost. No any extra payment shall be made for this

# Approvals Required

The Contractor shall obtain all Pre & all Post construction clearances/approvals from Environmental Authority, Municipal and other relevant statutory authorities/local bodies including Water supply agencies concerned, Electric Supply and inspectorate. Agencies concerned, such as, but not limited to, Police and Security Agencies, Chief Controller of Explosives, Fire Department, Civil Aviation Department, concerned in accordance to prevailing rules, Building Bye‐Laws, tree cutting etc., as the case may be with related to/ required for Construction/Completion. All expenditure on this account will be borne by the contractor. However, statutory payment on this account will be reimbursed by the client at actual on submission of documentary evidence of payment made. The status of applications for pre‐construction clearances submitted/applied to local authorities shall be provided to the contractor for obtaining clearances/approvals.

The approvals shall include the following in addition to any other approval which may be required for the project.

- Construction Permit if required

- NOC from Chief Fire Officer

- NOC from Lift Inspector where lifts are provided

- Occupancy certificate

- GRIHA Certification (Minimum 3 Star rating)

Assam PWD (Building)/Client may, at the written request of the Contractor, assist him in obtaining the approvals from relevant authorities. However any such request by the Contractor shall not bind the Assam PWD (Building) in any manner.

The contract comprises the construction, completion, remedying the defect of the works during defect liability period and except in so far as the Contract otherwise stipulates, the provision of all labour, materials, constructional plant, machinery temporary works and everything, whether of a temporary or permanent nature required in and for such construction, completion and maintenance so far as necessary for providing the same as specified in or reasonably to be inferred from the Contract.

# Order of Precedence of Documents:

In case of difference, contradiction, discrepancy, with regard to conditions of contract, Specifications, Drawings. Forming part of the contract, the following shall prevail in order of precedence.

- Letter of Intent (LOI)

- Any Amendment/Corrigendum issued.

- Schedule of Quantities & Rates (SOQR) and preamble to SOQR

- Design Basis Report (DBR) with Finishing Schedule & Matrix therein;

- Approved Construction Drawings by Client

- CPWD	Technical	Specification	and	other	Technical	Specifications	/ documents/ Relevant BIS Codes.

- Special Condition of Contract (SCC)

- General Condition of Contract (GCC)

- Notice Inviting e‐Tender (e‐NIT)

- Between two or more clauses of this contract, the provisions of specific clause relevant to the issue under consideration shall prevail over those in other clauses

- Between any two values written in numerals and in words, the latter shall prevail.

# A. Stage Payment Statement for Works

- Payment procedure as laid down by Govt of Assam will prevail.

- The Contractor shall base its claim for interim payment for the work executed till the end of the month for which the payment is claimed, supported with necessary particulars and documents in accordance with this Agreement. The basis of payment on "Pro rata basis" shall be worked out on the percentage of work done of total scope of work under their activity/item for the respective Cost Centre/Stage payment schedule. The contractor shall not be entitled to be paid any such interim payment if the gross work done together with net payment/ adjustment of advances for material collected, if any, since the last such payment is less than Rs.64.97 lakh, in which case the interim bill shall be prepared on the appointed date of the month after the requisite progress is achieved.

- The proportion assigned to an item will apply only to the Awarded Contract Price. It shall not apply to any additions or reductions to the Contract Price arising from the issue of any Change of Scope Order. A Change of Scope Order shall specify the stages of interim payments for the works covered by such order.

- The Contractor shall submit a statement (the "Stage Payment Statement")' in 3 copies, by the 7th (seventh) day of each month (statement for the previous month) to the Employer's Engineer in the. form as directed, showing the amount calculated to which the Contractor considers himself entitled for work executed under their activity/item for the respective Cost Centre/Stage payment schedule. The Stage Payment Statement shall be accompanied with the progress reports, at least two set of photographs and any other supporting documents & with the satisfaction of Engineer‐in‐charge.

- All such interim payments shall be regarded as payment by way of advances against final payment only and shall not preclude the requiring of bad, unsound and imperfect or unskilled work to be rejected, removed, taken away and reconstructed or re‐erected. Any certificate given by the Engineer‐in‐charge relating to the work done or materials delivered forming part of such payment, may be modified or corrected by any subsequent such certificate(s) or by the final payment certificate and shall not by itself be conclusive evidence that any work or materials to which it relates is/are in accordance with the contract and specifications. Any such interim payment, or any part thereof shall not in any respect conclude, determine or affect in any way powers of the Engineer‐in‐charge under the contract or any of such payments be treated as final settlement and adjustment of accounts or in any way vary or affect the contract.

# Final Bill Payment:

  - Within 60 (Sixty) days after receiving of the Completion Certificates and upon completion of all incomplete and outstanding works, the Contractor shall submit to the "Engineer‐in‐charge” for consideration six copies of a Final Payment Statement (the "Final Payment Statement") for Works, with supporting documents showing in detail, in the form prescribed by the Engineer‐ in‐charge

    - the summary of Contractor's Stage Payment bills for Works

    - the amounts received from the Employer/Assam PWD (Building) against each bill; and

    - any further sums which the Contractor considers due to it from the employer/ Assam PWD (Building)

If the Engineer‐in‐charge disagrees with or cannot verify any part of the Final Payment Statement, the Contractor shall submit such further information as the Engineer‐in‐ charge may reasonably require. The Engineer‐in‐charge shall deliver to the Employer:

- an IPC for those parts of the Final Payment Statement which are not in dispute, along with a list of disputed items which shall then be settled in accordance with the provisions of contract; or

- Final Payment Certificate if there are no disputed items.

# Final Payment Certificate:

  - Within 90 (Ninety) days after receipt of the Final Payment Statement for Works, and the written discharge, and there being no disputed items of claim, the Engineer‐in‐ charge shall deliver to the Employer, with a copy to the Contractor, a final payment certificate (the "Final Payment Certificate") stating

    - the amount which, in the opinion of the Engineer‐in‐charge, is finally due under this Agreement or otherwise; and

    - after giving credit to the Employer for all amounts previously paid by the Employer and for all sums to which the Employer is entitled, the balance, if any, due from the Employer to the Contractor or from the Contractor to the Employer as the case maybe.

  - The Employer shall pay to the Contractor the amount which is finally due, less all amounts previously paid by the Employer/Assam PWD (Building) and any deductions for the amounts the Employer considers itself to be entitled in accordance with this Agreement, and shall provide the particulars thereof to the Contractor.

# Production of Records:

- The Contractor shall, whenever required by the Engineer, produce or cause to be produced for examination by the Engineer, any quotation, invoice, cost or other account books, vouchers, receipts, letters, memoranda or any copy of or extract from any such documents and also furnish information and returns, as may be required, relating to the execution of this Contract or relevant for verifying ascertaining the cost of execution of this Contract or ascertaining the Materials supplied Contractor are in accordance with the Specifications laid down in the contract. The Engineers in charge’s decision on the question of relevancy of any document information or returns shall be final and binding on the parties.

- If any part or item of the work is allowed to be carried out by a subcontractor, assignee or any subsidiary or allied firm, the Engineer‐in‐charge shall have power to secure the books of such sub‐ Contractor, assignee or any subsidiary or allied firm through the Contractor, and shall have power to examine and inspect the same. The above obligations are without prejudice to the obligations of the Contractor under any statute, rules or order.

- The Preparation of design/drawings & bill of quantities (of his stated scope of work) etc.: Bar Bending Schedule, Shop & Fabrication drawings for all work shall be supplied by the Contractor as per agreed schedule/ as the work progresses. However, it shall be the duty and responsibility of the Contractor to bring to the notice of the Assam PWD (Building) in writing as to any variation, discrepancy or any other changes required in Drawing, design etc. whether of Assam PWD (Building) Scope or Contractor's Scope of work and to obtain/prepare (as the case may be) revised drawings and designs and/ or approval of the Assam PWD (Building) in writing for the same .

- The contractor shall have to obtain all Pre & Post Approvals including Connections/ NOCs/ Completion Certificates/ Occupancy Certificate, etc from the concerned Local/Statutory authorities for Sewerage works, Water Supply works, Fire Fighting work, Fire Alarm system work, DG set /pollution clearance, lift, Forrest etc. at his own cost and nothing extra other than statutory fee/charges shall be payable on this account to the contractor. However, the letters required from the owner for the needful stated purposes will be arranged by Assam PWD (Building) from the owner as per the request of contractor along with the statutory charges/fee

demanded by the local/statutory authorities.

- Tenderers are advised to inspect and examine the site and its surroundings and satisfy themselves before submitting their tenders as to the nature of the ground and sub‐soil (so far as is practicable), the form and nature of the site, the means of access to the site, the accommodation they may require and in general shall themselves obtain all necessary information as to risks, contingencies and other circumstances which may influence or affect their tender. A bidder shall be deemed to have full knowledge of the site whether he inspects it or not and no extra charges consequent on any misunderstanding or otherwise shall be allowed/payable. The bidder shall be responsible for arranging and maintaining at its own cost all materials, tools & plants, water, electricity, access, facilities for workers and all other services required for executing the work unless otherwise specifically provided for in the contract documents. Submission of a tender by a bidder implies that he has read this notice and all other contract documents and has made himself aware of the scope and specifications of the work to be done and of conditions and rates at which stores, tools and plant, etc. will be issued to him by the Government and local conditions and other factors having a bearing on the execution of the work.

# Site office and Infrastructure

A reasonably furnished of site office area about 150 sqmt. having a sample room, A.C. meeting room, A.C. staff rooms with file storage facility along with computers & printers and its consumables, a telephone with STD facility, Fax Machine, internet and toilets & pantry and vehicle (s) 1 numbers (Swift Dzire or equivalent) complete with driver, fuel and consumables and furnished transit accommodation (having minimum 3 BHK) shall be provided for Executing agency/Assam PWD (Building) by the Contractor at his own cost for the duration of the Contract. Electricity & drinking water for the site office will have to be provided by the contractor at his own cost for the site office.

In case suitable existing building/accommodation is available at site, the same may be furnished as above with the consent of the Executing Agency.

# Testing facilities

The Contractor/EPC shall, at his own cost, provide testing facilities as per CPWD scale and IS Codes at site as stipulated in the CPWD Works manual / as per Contract document or as directed by the Executing Agency/Engineer‐in‐charge.

The laboratory shall be equipped and manned by the Contractor at his own cost with all necessary apparatus to carry out the above mentioned tests in accordance with relevant Indian Standards or equivalent approved Standards. Contractor/EPC agency shall bear the cost of four (04) nos. qualified engineer having experience of 3 years on role of Assam PWD (Building) for quality control of works. The same may be replaced/terminated as per discretion of Assam PWD (Building).

  - Cement testing:

Tests for fineness, Strength, setting time and soundness in accordance with IS:4031.

  - Concrete Testing:

Test for workability, proportions, density and strength in accordance with IS:516 and 1199. In particular the cube testing machine shall be cable of exerting a slowly applied force up to 200 tonnes and the platens shall be suitable for crushing both 150mm and 200 mm cubes. A Vibrating table of suitable design shall be provided for compaction of cubes.

  - Aggregate Testing:

In accordance with IS: 2386 (part I to VIII) for the following tests on both fine and coarse aggregates:

    - Sieve analysis

    - Determination of bulk density and voids on fine aggregates only:

    - Determination of moisture content, specific gravity and absorption on coarse aggregates only:

    - Determination of specific gravity and absorption

The contractor shall carryout inspection, testing, checks and also shall maintain records of inspection, testing & checks of material, works and activities related to construction works in the ISO 9001 quality system formats, checklists etc. to be given by Executing Agency during execution period. After getting approval from the Engineer, The contractor shall print at his own cost all forms, tables, formats etc.

The laboratory shall be connected to the main water and electricity Services. It shall also be supplied with portable gas equipment.

On completion of the project, the laboratory is to be dismantled and removed from Site. The dismantled materials and equipment shall be the property of the Contractor.

In case certain tests are to be carried out in approved outside laboratory, as stipulated in the contract document / as directed by the Executing Agency, the Contractor shall bear the entire cost including samples, taking samples, testing, reports etc.

# Guarantee/Warranty

All plant/ equipments/ machinery installed/commissioned shall be guaranteed or warrantee (as per applicability of guarantee/warranty given in technical specifications for each plant/ equipments/ machinery) for a period of 24 months (minimum) from the date of acceptance and taking over of the installation by Assam PWD (B) against un‐ satisfactory performance and/or breakdown due to defective design, material, manufacture, workmanship or installation. The guarantee/warranty period given above is the minimum period for which a plant/equipments/machinery is required to be covered under guarantee/warranty. However, if required guarantee/warranty period in technical specification is specified more than 24 month for any plant/equipments/machinery from the date of acceptance and taking over of the installation by Assam PWD (B); then the higher period will be the required period of guarantee/warranty for that particular plant/ equipments /machinery. The plant/equipments/machinery or component or any part thereof so found defective during the guarantee/warranty period shall be repaired or replaced free of cost to the satisfaction

of the Engineer in‐charge/Project Manager. In case it is felt by Assam PWD (B) that undue delay is being caused by the contractor in doing this, the same will be got done by Assam PWD (B) at the risk and cost of the contractor. The decision of Engineer‐in‐charge in this regard shall be final.

# Diversion of Services

All works pertaining to services including rerouting/diversion of services, routine testing, installation etc., embracing in one or more than one process shall be subject to examination and approval to each stage thereof by the Engineer‐in‐charge or concerned department as would be notified by the Engineer‐in‐charge or his accredited representative when such stage is ready. In default of such notice, the Engineer‐in‐ Charge shall be entitled to appraise the quantity and extent thereof and the decision of Engineer‐in‐Charge or his accredited representative in this regard shall be final and binding.

The contractor will not have any claim in case of any delay in removal of trees or shifting, raising, removing of telegraph, telephone or electric lines (overhead or underground), water and sewer lines and other structures etc., if any, which may come in the way of the work.

# Disposal of surplus excavated earth/ Spoils

The Contractor shall be deemed to have taken into account the quantum of excavation involved and that the surplus excavated earth remaining after use in operations such as Horticulture/Landscaping, Gardening, backfilling etc. and to be disposed‐off by him; shall become his property free of cost.

It will be the responsibility of the Contractor to get the permission for yard for dumping the surplus excavated earth from local authority if required. If any royalty/fee is payable to local authority, such royalty/fee shall also be borne by the Contractor. Disposal shall be carried out strictly as per the regulations of local authority.

The contractor shall store the excavated earth required for operations such as Horticulture/Landscaping, Gardening, backfilling etc., at his own place other than the project site under his safe custody at his own cost. Thereafter, the earth so stored shall be backfilled at site at the appropriate time. The cost of storage, transportation (to & from site), handling etc. shall be borne by the contractor.

The Contractor shall also be deemed to have taken into account the credit to be given to Assam PWD (B). in his quoted price for such surplus earth obtained free of cost. Contractor has to preserve 300 mm top layer as mandated in GRIHA.

The contractor shall also make his own arrangement for the disposal of the spoils from the works to such place where the same shall not cause nuisance and should be acceptable to the authorities concerned without any cost to Assam PWD (B).

# Unforeseen Difficulties

Except as otherwise specifically stated elsewhere in the Contract:

- The Contractor shall be deemed to have obtained all necessary information as to risks, contingencies and other circumstances which may influence or affect the Works;

- By signing the Contract, the Contractor accepts total responsibility for having foreseen all difficulties and costs of successfully completing the Works; and

- The Contract Price shall include all the works mentioned Scope of work, Design basis

reports (DBR), technical specifications, Concept / tender Drawings, tender documents etc. covering the entire area in all respect to make the buildings & complex fit for its intended purpose i.e. handing over for functional use as hospital and not be adjusted to take account of any unforeseen difficulties or costs.

Assam PWD (B) shall not provide any material either on chargeable or on free issue basis to the contractor for execution of the project.